## Info
Epic Gold System Policy Analysis and Action Plan
Purpose: This workflow aims to enhance collaboration between System Clinical Informaticists (SCI) and Application Analysts to accurately identify, prioritize, and remediate missing System Policy components within Epic Gold. The goal is to ensure the current build precisely mirrors the requirements outlined in CSH policy, fostering data integrity and operational efficiency.
Target Audience: SCI, SCI Managers, Application Analyst Managers, and Application Analysts
Please DO NOT edit formulas without SCI involvement
Workflow Steps:
1. CI Identification of Missing Component(s)
SCI review CSH policy to Epic Gold build and identify discrepancies related to existing System Policy requirements
2. SCI Manager Priority Assessment
The SCI Manager review and prioritize each missing component
3. Analyst Manager Assignment
The Application Analyst Manager assigns each task to the appropriate Primary Application Analyst
4. Primary Analyst & SCI Collaboration
The assigned Primary Analyst and Primary SCI collaborate closely to define the detailed build requirements and scope. Involving: Establishing meeting cadence (collaborative calls, email, etc.) for efficient collaboration for all participants Identifying Epic records that need to be created, modified, or removed Evaluate potential downstream impacts of requested changes Engaging other module analysts as needed Involving key stakeholders if further decisions are required (SCI) Identifying if end-user education is required with the change
5. Analyst and SCI Tracking and Progress
Accurately document status, milestones, roadblocks, and escalations within the Master Missing Components Log The Primary Analyst is responsible for tracking the build progress of their assigned tasks within their individual spreadsheet The SCI is responsible for tracking information on the Master Missing Components Log and any decisions pertaining to the required build Note: Update any Orion tasks associated with the build if applicable
6. Weekly Updates for Management
Before end of day Friday, update tracker with any relevant data related to the task

## Initiatives
id | name | description | type | priority | primarySCI | secondarySCI | applications | venues | rolesImpacted | systemSponsor | goLiveWave | policyLink | ehrRequirementsLink | status | createdDate | updatedDate
EG-0002 | Nursing Travel Screening Assessment | Need Foundation Travel Screening within Admission Navigator and Required Documentation | Standard Practice | High | Brooke Snow | Marisa Radick | Clindoc | Acute Inpatient | Nursing | Alison Mason | Wave 3 |  |  | In Progress | 2026-03-11T20:52:08.868Z | 2026-03-11T21:30:30.721Z
EG-0003 | Candida auris |  | Guideline | High | Brooke Snow |  |  |  |  | Becky Leach | Wave 3 |  |  | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T21:41:56.800Z
EG-0004 | Nursing Head to Toe Assessment | Basic assessment flowsheet is missing rows related to the neurology and cardiac assessments | Standard Practice | High | Brooke Snow | Marisa Radick | Clindoc |  |  | Alison Mason | Wave 3 |  |  | In Progress | 2026-03-11T20:52:08.868Z | 2026-03-11T21:24:49.931Z
EG-0006 | Nursing Fall Assessment | Can only document interventions on the Screenings Flowsheets, not within the Daily Cares Flowsheet | Policy | High | Brooke Snow | Marisa Radick | Clindoc |  |  | Alison Mason | Wave 3 |  |  | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T21:28:15.466Z
EG-0007 | Nursing Skin Assessment | an only document interventions with the Braden, not the BradenQ | Standard Practice | High | Brooke Snow | Marisa Radick | Clindoc | Acute Inpatient | Nursing | Alison Mason | Wave 3 |  |  | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T21:31:38.118Z
EG-0008 | Suicide Policy |  |  | High | Jason Mihos |  | Clindoc | [6 empty] | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0009 | ED SOP |  |  | High | Jason Mihos |  | ASAP, Clindoc | [6 empty] | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0010 | Bladder Management |  |  | High | Trudy Finch |  | Clindoc, Orders | [6 empty] | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0011 | SDOH | SDOH needs standard implementation across storyboard, flowsheets, OPAs, AVS. Includes the addition of nursing intervention documentation for positive IPV responses. | Standard Practice | High | Marty Koepke |  |  | ED,Acute Inpatient,Ambulatory | Provider,Nursing,Medical Assistants,Care Coordination,Social Work | Ankita Sagar | Wave 3 |  |  | Under Review | 2026-03-11T20:52:08.868Z | 2026-03-11T21:00:53.149Z
EG-0012 | Nursing SOP - Dialysis Graft/Fistula | AV Fistula and AV Graft LDAs require need additional selections. | Standard Practice | High | Brooke Snow | Marisa Radick | Clindoc |  |  | Alison Mason | Wave 3 |  |  | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T21:34:34.143Z
EG-0013 | Sedation Policy Narrator |  |  | Medium | Sherry Brennaman |  | Clindoc, ASAP, Rad, Lumens, Optime | [6 empty] | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0014 | Suicide Policy Dashboards |  |  | Medium | Jason Mihos |  | Clindoc, Reporting | [6 empty] | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0015 | Preferred Languages |  |  | Medium | Marisa Radick |  | Grand Central | [6 empty] | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0016 | ICU Liberation |  |  | Medium | Marisa Radick |  | Clindoc | [6 empty] | In Progress | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0017 | Valubles & Belongings |  |  | Medium | Melissa Plummer |  | Clindoc, ASAP, OpTime | [6 empty] | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0018 | DAST10 |  |  | Medium | Melissa Plummer |  | Stork | [6 empty] | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-11T20:52:08.868Z
EG-0019 | Amb Depression Screening |  |  | High | Marty Koepke |  |  | Ambulatory | Medical Assistants,Provider | Deb Rockman | Wave 3 |  |  | In Progress | 2026-03-11T22:14:21.112Z | 2026-03-11T22:14:21.112Z
EG-0020 | Amb BP - 2nd Reading for 140/90 | Discovery needed. System guideline indicates we need a 2nd BP reading for BP 140/90+. We see red for awareness, but no downstream alerting to retake a 2nd pressure during the amb encounter. | Guideline | High | Marty Koepke |  |  | Ambulatory | Provider,Medical Assistants | Deb Rockman | Wave 3 |  |  | Under Review | 2026-03-11T22:17:32.236Z | 2026-03-11T22:17:32.236Z

## Tasks
id | initiativeId | description | module | priority | primaryAnalyst | additionalAnalysts | status | educationRequired | buildReviewComplete | buildReviewDate | resolutionDate | createdDate
TSK-0005 | EG-0002 | Add in Foundation Travel screening to all admission navigators - FS Travel screening already aligns with Legacy Epic workflows | ClinDoc | High | Alex Cordell |  | Analyst Assigned | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0006 | EG-0003 | Provider OPA: An interruptive OPA when a high risk patient is admitted. |  | High |  |  | Identified | No | In Progress |  |  | 2026-03-11T20:52:08.868Z
TSK-0007 | EG-0004 | Neuro: Include LOC, Orientation Status, Facial symmetry, Speech, Cental nerves (corneal, cough, gag), DTR |  | High | Alex Cordell |  | Analyst Assigned | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0009 | EG-0006 | Add flowsheet rows for Fall Interventions in the Daily Cares flowsheet | ClinDoc | High | Alex Cordell |  | Identified | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0010 | EG-0007 | Add Intervention documentation to the BradenQ. |  | High |  |  | Identified | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0011 | EG-0008 | Clindoc — [Legacy ID: MCI-0007] — (Detailed Description/Missing Fields: Social work/care coordination - CSSRS initial Screening OB - Are they using CSSR processes or DAST10? ¦ Analyst/SCI Initial Build Review Complete: No - Did not meet with analyst ¦ Notes: For social work/care coordination, initial CSSRS access/documentation not needed -- this is done by nurses Regarding OB: DAST-10 is a drug-abuse screening tool, is not equivalent to Columbia suicide risk screen. System suicide risk policy applies to all acute areas and warrants use of CSSRS/Columbia tools, so this is what OB should be using) | Clindoc | High |  |  | Identified |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0012 | EG-0009 | ASAP, Clindoc — [Legacy ID: MCI-0008] — (Detailed Description/Missing Fields: Abuse/neglect, violence screening -- neglect not included ¦ Analyst/SCI Initial Build Review Complete: No - Did not meet with analyst) | ASAP, Clindoc | High |  |  | Identified |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0013 | EG-0010 | Clindoc, Orders — [Legacy ID: MCI-0009] — (Detailed Description/Missing Fields: Indications missing Epidural in Place, remove "Provider Managed" Nurse is able to place an IUC without a LIP Order. Not a clear place to document alternative management strategies attempted Order for Urinary Catheter does not have any required 'Criteria for Use' documentation requirements ¦ Analyst/SCI Initial Build Review Complete: No - Did not meet with analyst ¦ Action Items for Resolution: Need orders analyst identified) | Clindoc, Orders | High |  |  | Identified |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0014 | EG-0011 | Storyboard access to Social Drivers provided for ED, Acute, Amb, HOD |  | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T20:52:08.868Z
TSK-0015 | EG-0011 | CMS AHS core Social Drivers questions as well as Nursing Interventions need to be available in relevant flowsheets. Observation of harm question and nursing intervention questions need to be clearly labeled as RN only. The desire is to leverage same flowsheet ID for all areas, if possible. |  | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T20:52:08.868Z
TSK-0016 | EG-0011 | OPA needs for referral to SW on + IPV responses (Acute and ED) |  | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T20:52:08.868Z
TSK-0017 | EG-0011 | OPA for SW when patient responds to desiring assistance to non safety questions. (ED/Acute) |  | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T20:52:08.868Z
TSK-0018 | EG-0012 | AV Fistula can only select one option for Thrill, bruit, Absent, Present - Should this be multi-select | ClinDoc | High | Corrinne Welch |  | Identified | No | In Progress | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0019 | EG-0013 | Clindoc, ASAP, Rad, Lumens, Optime — [Legacy ID: MCI-0015] — (Detailed Description/Missing Fields: Vital Signs - Missing ECO2 Waveform Pre-Procedure Checklist (ED) Rad Studies Available? Beta Blocker VTE Prophylaxis Normothermia Measures Stop Bang Sign In / Briefing - Missing Time Out Sign Out or Debriefing - Missing ¦ Analyst/SCI Initial Build Review Complete: No - Did not meet with analyst) | Clindoc, ASAP, Rad, Lumens, Optime | Medium |  |  | Identified |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0020 | EG-0014 | Clindoc, Reporting — [Legacy ID: MCI-0016] — (Detailed Description/Missing Fields: ED key metrics dashboard OB nurse manager dashboard Inpt quality nurse ¦ Analyst/SCI Initial Build Review Complete: No - Did not meet with analyst ¦ Notes: To my understanding, in February were still being built) | Clindoc, Reporting | Medium |  |  | Identified |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0021 | EG-0015 | Grand Central? — [Legacy ID: MCI-0017] — (Detailed Description/Missing Fields: Missing Languages: Persian Navajo Slightly Different Spelling: Punjabi (Spelled Panjabi) Urdu (Written as Urdu Pakistan) ¦ Analyst/SCI Initial Build Review Complete: No - Did not meet with analyst) | Grand Central? | Medium |  |  | Identified |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0022 | EG-0016 | Clindoc — [Legacy ID: MCI-0018] — (Detailed Description/Missing Fields: SAT Safety Screen SBT Safety Screen Early Progressive Mobility Protocol: Screen for Safety Daytime/Nightime Interventions - does this need to be documented in EHR? ¦ Analyst/SCI Initial Build Review Complete: Yes - Build can be complete ¦ Analyst/SCI Build Review Meeting Date: 2026-02-11T08:00:00.000Z ¦ Action Items for Resolution: Sent two corrections back over to Sara on 2/26, awaiting her response to perform a final review) | Clindoc | Medium | Sara Garcia |  | Build In Progress |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0023 | EG-0017 | Clindoc, ASAP, OpTime — [Legacy ID: MCI-0019] — (Detailed Description/Missing Fields: Policy Screenshots provided) | Clindoc, ASAP, OpTime | Medium |  |  | Identified |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0024 | EG-0018 | Stork — [Legacy ID: MCI-0020] — (Detailed Description/Missing Fields: The DAST-10 tool is only found when searching the Database in Flowsheets Provider Notification also does not display and is only found in the Database when looking for Flowsheets Neither of the options when displayed in Flowsheets contains the Interventions as seen in FHS and CEN) | Stork | Medium |  |  | Identified |  |  |  |  | 2026-03-11T20:52:08.868Z
TSK-0025 | EG-0011 | OPA design needed for positive IPV responses, to provider on that visit encounter, to inform provider of + responses |  | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T21:10:29.521Z
TSK-0026 | EG-0011 | OPA needed to remind MAs to provide community referral when patient responds yes to wanting assistance on non harm questions. |  | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T21:11:30.645Z
TSK-0027 | EG-0011 | After Visit Summary alignment to provide link to Find Help (add URL), on AVS where SDOH screenings are performed. (ED, Acute, Amb, HODs) |  | High |  |  | Identified | No | In Progress | 2026-03-10 |  | 2026-03-11T21:12:46.470Z
TSK-0028 | EG-0004 | Cardiac: Update Cardiac Symptoms to include chest pain Update Chest Tubes LDA for patency Include Implantable Cardiac Defibrillators rows | ClinDoc | High | Alex Cordell |  | Identified | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T21:26:54.456Z
TSK-0029 | EG-0012 | AV Graft needs the option to document Thrill, bruit, Absent, Present | ClinDoc | High | Corrine Welch |  | Identified | No | In Progress | 2026-02-11 |  | 2026-03-11T21:36:09.731Z
TSK-0030 | EG-0003 | IP and Nursing OPA: A Storyboard OPA when a high risk patient is admitted. |  | Medium |  |  | Identified | No | In Progress |  |  | 2026-03-11T21:41:27.915Z
TSK-0031 | EG-0020 | PHQA needs OPA when score is >4 |  | High |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-11T22:23:38.949Z
TSK-0032 | EG-0019 | OPA needed for positive PHQA for provider to do an interpretation and follow up plan if needed |  | High |  |  | Identified | Yes | No - Did not meet with analyst |  |  | 2026-03-11T22:36:24.845Z

## TaskNotes
id | taskId | timestamp | author | noteText | noteType
NTE-0001 | TSK-0014 | 2026-03-11T21:17:23.133Z | mkoepkeci@gmail.com | Met with corrine and 2 others to review this. | General

## TaskActionItems
id | taskId | description | owner | dueDate | status | completedDate | notes | createdDate
TAI-0002 | TSK-0031 | Confirm the correct score for triggering an OPA on PHQA | Marty Koepke |  | Not Started | 2026-03-11T22:25:26.315Z |  | 2026-03-11T22:25:05.899Z
TAI-0003 | TSK-0032 | Confirm with Kelly Bitonio the correct score for triggering interpretation on PHQA | Marty Koepke | 2026-03-13 | In Progress |  |  | 2026-03-11T22:36:52.791Z

## TaskDocuments
id | taskId | documentName | documentType | url | dateAdded

## PRCC_Config
key | value
nextInitiativeId | 22
nextTaskId | 33
nextTaskNoteId | 2
nextTaskActionItemId | 4
nextTaskDocumentId | 1
nextTaskActionItemId | 1
nextTaskDocumentId | 1

## Master Missing Components Log
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Resolution Date | Notes
MCI-0001 | Nursing SOP Travel Screening | Need Foundation Travel Screening within Admission Navigator and Required Documentation | Clindoc | High | Alex Cordell | Brooke Snow | Analyst Assigned | No | Yes - Build can be complete | 2026-02-11 | Add in Foundation Travel screening to all admission navigators - FS Travel screening already aligns with Legacy Epic workflows
MCI-0002 | Candida auris | Candida auris screening OPA workflow | Primary - OPA Multiple Teams: Provider, Nurisng, Bugsy, reporting, Registration, HB | High |  | Brooke Snow | Identified | No | No - Did not meet with analyst |  |  |  | Working with OPA, Nursing, Infection Prevention/Bugsy, Reporting, Registration and HB analyst managers on resource identification This build went live in Legacy Epic 2/24/26 and is live in Cerner ECISA/CAREB in Janurary
MCI-0003 | Nurisng SOP Basic Neuro Assessment | Include LOC, Orientation Status, Facial symmetry, Speech, Cental nerves (corneal, cough, gag), DTR | Clindoc | High | Alex Cordell | Brooke Snow | Analyst Assigned | No | Yes - Build can be complete | 2026-02-11
MCI-0004 | Nurisng SOP Basic Cardiac Assessment | Update Cardiac Symptoms Update Chest Tubes LDA Include Implantable Cardiac Defibrillators | Clindoc | High |  | Brooke Snow | Identified | No | No - Did not meet with analyst
MCI-0005 | Nurisng SOP Fall Assessment | Fall interventions | Clindoc | High |  | Brooke Snow | Identified | No | No - Did not meet with analyst
MCI-0006 | Nursing SOP Skin | Intervention documentation mismatch | Clindoc | High |  | Brooke Snow | Identified | No | No - Did not meet with analyst
MCI-0007 | Suicide Policy | Social work/care coordination - CSSRS initial Screening OB - Are they using CSSR processes or DAST10? | Clindoc | High |  | Jason Mihos | Identified |  | No - Did not meet with analyst |  |  |  | For social work/care coordination, initial CSSRS access/documentation not needed -- this is done by nurses Regarding OB: DAST-10 is a drug-abuse screening tool, is not equivalent to Columbia suicide risk screen. System suicide risk policy applies to all acute areas and warrants use of CSSRS/Columbia tools, so this is what OB should be using
MCI-0008 | ED SOP | Abuse/neglect, violence screening -- neglect not included | ASAP, Clindoc | High |  | Jason Mihos | Identified |  | No - Did not meet with analyst
MCI-0009 | Bladder Management | Indications missing Epidural in Place, remove "Provider Managed" Nurse is able to place an IUC without a LIP Order. Not a clear place to document alternative management strategies attempted Order for Urinary Catheter does not have any required 'Criteria for Use' documentation requirements | Clindoc, Orders | High |  | Trudy Finch | Identified |  | No - Did not meet with analyst |  | Need orders analyst identified
MCI-0010 | SDOH | Social Drivers available in Storyboard for ED, Acute IP, Amb, Other HODs like OP Surgery, Infusion Centers. |  | High |  | Marty Koepke | Identified |  | Yes - Met with Analyst, Further build review needed | 3.10.26
MCI-0011 | SDOH | Social Drivers and Nursing Intervention questions available in Flowsheets for ED, Acute IP, Amb, Other HODs like OP Surgery, Infusion Centers. |  | High |  | Marty Koepke | Identified |  | Yes - Met with Analyst, Further build review needed | 3.10.26 | "Needs design review. Core CMS questions + observation of abuse question + nursing intervention questions available for RNs Only. Easiest conceived design is to have a single flowsheet that has all elements, with clear RN Only headers for Observation and nursing intervention sections. Needs some review. Appears that correct Social Drivers screening flowsheet has not been applied appropriately across positions/venues. EDRN in Gold TST do not have the correct flowsheet applied to preference list. "
MCI-0012 | SDOH | OPA work needed: - Acute/ED - Auto fire SW OPA when harm question answered + - Acute/ED - Auto fire SW OPA when patient answers + to wanting help for non safety questions. - Amb/HOD - Auto fire awareness OPA for providers when harm questions answered + - Amb/HOD - Auto fire awareness OPA to alert staff to place community referral |  | High |  | Marty Koepke | Identified |  | Yes - Met with Analyst, Further build review needed | 3.10.26 | Need best practice recommendation to alert providers that patient responded + to harm question, and/or are asking for support to non harm questions. Also to alert staff to create a community referral when patient is asking for support to non harm items.
MCI-0013 | SDOH | AVS - Add Find Help URL - All venues (ED, Acute, Amb, OP Depts where SDOH is screened) |  | High |  | Marty Koepke | Identified |  | Yes - Met with Analyst, Further build review needed | 3.10.26 | Need to determine if a print group for this exists for acute IP Gold.
MCI-0014 | Nursing SOP - Dialysis Graft/Fistula | Bruit/Thrill documentation for Graft/Fistulas | Clindoc | Medium | Corrinne Welch | Brooke Snow | Identified | No | No - Did not meet with analyst
MCI-0015 | Sedation Policy Narrator | Vital Signs - Missing ECO2 Waveform Pre-Procedure Checklist (ED) Rad Studies Available? Beta Blocker VTE Prophylaxis Normothermia Measures Stop Bang Sign In / Briefing - Missing Time Out Sign Out or Debriefing - Missing | Clindoc, ASAP, Rad, Lumens, Optime | Medium |  | Sherry Brennaman | Identified |  | No - Did not meet with analyst
MCI-0016 | Suicide Policy Dashboards | ED key metrics dashboard OB nurse manager dashboard Inpt quality nurse | Clindoc, Reporting | Medium |  | Jason Mihos | Identified |  | No - Did not meet with analyst |  |  |  | To my understanding, in February were still being built
MCI-0017 | Preferred Languages | Missing Languages: Persian Navajo Slightly Different Spelling: Punjabi (Spelled Panjabi) Urdu (Written as Urdu Pakistan) | Grand Central? | Medium |  | Marisa Radick | Identified |  | No - Did not meet with analyst
MCI-0018 | ICU Liberation | SAT Safety Screen SBT Safety Screen Early Progressive Mobility Protocol: Screen for Safety Daytime/Nightime Interventions - does this need to be documented in EHR? | Clindoc | Medium | Sara Garcia | Marisa Radick | Build In Progress |  | Yes - Build can be complete | 2026-02-11 | Sent two corrections back over to Sara on 2/26, awaiting her response to perform a final review
MCI-0019 | Valubles & Belongings | Policy Screenshots provided | Clindoc, ASAP, OpTime | Medium |  | Melissa Plummer | Identified
MCI-0020 | DAST10 | The DAST-10 tool is only found when searching the Database in Flowsheets Provider Notification also does not display and is only found in the Database when looking for Flowsheets Neither of the options when displayed in Flowsheets contains the Interventions as seen in FHS and CEN | Stork | Medium |  | Melissa Plummer | Identified

## Analyst Dashboard
Summary
Total Open Items | 18
Total Critical Items | 0
Total High Priority Items | 13
Items in Build in Progress | 1
Items Closed - Completed | 0
Items Closed - Deferred | 0
Breakdown by Analyst
Owner | Total Assigned | Open | Critical Open | Closed
Alex Cordell | 2 | 2 | 0 | 0
Amanda Davidson | 0 | 0 | 0 | 0
Christi Allen | 0 | 0 | 0 | 0
Christi Elsmore | 0 | 0 | 0 | 0
Corrinne Welch | 1 | 1 | 0 | 0
Gary Hudson | 0 | 0 | 0 | 0
Karan Patel | 0 | 0 | 0 | 0
Karen Sykes | 0 | 0 | 0 | 0
Kate Glass | 0 | 0 | 0 | 0
Maria Delacruz | 0 | 0 | 0 | 0
Mary Eckert | 0 | 0 | 0 | 0
Matthew Walsh | 0 | 0 | 0 | 0
Myra Ventrcek | 0 | 0 | 0 | 0
Pam Shadle | 0 | 0 | 0 | 0
Patrick McGovern | 0 | 0 | 0 | 0
Racquel Calhoun | 0 | 0 | 0 | 0
Ryan Carr | 0 | 0 | 0 | 0
Sara Garcia | 1 | 1 | 0 | 0
Sheron Johnson | 0 | 0 | 0 | 0

## Amanda Davidson
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Other Modules/Analyst | Downstream Impacts | Affected Epic ID's | Build Questions

## Alex Cordell
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Other Modules/Analyst | Downstream Impacts | Affected Epic ID's | Build Questions
MCI-0001 | Nursing SOP Travel Screening | Need Foundation Travel Screening within Admission Navigator and Required Documentation | Clindoc | High | Alex Cordell | Brooke Snow | Analyst Assigned | No | Yes - Build can be complete | 02/11/2026 | Add in Foundation Travel screening to all admission navigators - FS Travel screening already aligns with Legacy Epic workflows | Gold Build: EHR Content Review- Core Nursing SOP | Beaker - John Snow Bugsy - Shawn Johnson
MCI-0003 | Nurisng SOP Basic Neuro Assessment | Include LOC, Orientation Status, Facial symmetry, Speech, Cental nerves (corneal, cough, gag), DTR | Clindoc | High | Alex Cordell | Brooke Snow | Analyst Assigned | No | Yes - Build can be complete | 02/11/2026 |  | Gold Build: EHR Content Review- Core Nursing SOP

## Christi Allen
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Christi Elsmore
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Corrine Welch
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions
MCI-0014 | Nursing SOP - Dialysis Graft/Fistula | Bruit/Thrill documentation for Graft/Fistulas | Clindoc | Medium | Corrinne Welch | Brooke Snow | Identified | No | No - Did not meet with analyst

## Gary Hudson
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Karan Patel
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Karen Sykes
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Kate Glass
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Maria Delacruz
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Mary Eckert
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Matthew Walsh
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Myra Ventrcek
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Pam Shadle
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Patrick McGovern
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Racquel Calhoun
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Ryan Carr
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Sara Garcia
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions
MCI-0018 | ICU Liberation | SAT Safety Screen SBT Safety Screen Early Progressive Mobility Protocol: Screen for Safety Daytime/Nightime Interventions - does this need to be documented in EHR? | Clindoc | Medium | Sara Garcia | Marisa Radick | Build In Progress |  | Yes - Build can be complete | 2/11/26 | Sent two corrections back over to Sara on 2/26, awaiting her response to perform a final review

## Sheron Johnson
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Archived Components
ID | Missing Component | Detailed Description | Module | Priority | Primary Analyst | Primary SCI | Status | Downstream Impacts | Affected Epic ID's | Build Questions | Resolution Date | Action Items for Resolution | Notes
| Oral Kleen | Missing Oral Mucisal care and Tongue Scraping | Clindoc | Medium |  | Sherry Brennaman | Closed - Completed | [5 empty] | Crosswalk
| Age Friendly | Turbocharger package needed;expanded SDOH questions with age based criteria; | Multiple Apps | High |  | Dawn Jacobson | Closed - Deferred

## CSH PSG
IT Indicated in Gold | System Policy/Standard/Guideline | Type | Priority | Confirmed in Gold (Validated) | SCI Point of Contact | Analyst | Application | Specialty/Primary Impacted Dept./Discipline | Specialized Workflow Needed? | Brief Details | Link to Policy/ Guideline | Intake Slide | Link to Document/ EHR Requirements | System Sponsor | Comments/Follow-up | CSH Standards of Practice - https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice
| E-Signature in Epic Templates |  | 1 |  | Ashley Hubbard |  | Orders | Provider/Nursing
| Antimicrobial Steardship for ARTIs |  | 1 |  | Ashley Hubbard |  | Willow / Orders | Pharmacy | No
| C-Auris | Guideline | 1 | No | Brooke Snow |  | Clin Doc / Orders | Provider/Nursing | Yes |  |  | System Initiative Candida auris | Candida auris _SCI Workbook | Becky Leach | Each Epic instance has slightly different build - need to finalize build and workflow with Bugsy piece included in order to finalize Gold build
| Core Nursing - Standard of Practice |  | 1 | Yes | Brooke Snow & Marisa Radick |  | Clin Doc | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice CommonSpirit Core Nursing Standards of Practice.docx |  | Gold Build: EHR Content Review- Core Nursing SOP
| Yale Swallow Screen | Policy | 1 | Yes | Dawn Jacobson |  | Clin Doc | Provider/Nursing | No | Via email on 11/20. Christi confirmed in Gold, and will remove TF as exclusion criteria. 2.11 - Stroke Narrator does not contain Yale Swallow Screening. ASAP team is replacing the current screening documentation with Yale for Wave 3.
| Age Friendly Documentation | Board Goal | 1 | No | Dawn Jacobson |  | Clindoc | Provider/Nursing | Yes
Yes | Suicide Risk Policy | Policy | 1 | Yes | Jason & Sherry |  | Clin Doc | BHU/Nursing | Yes | See details. Note: No decisions yet as to which dashboards in Epic Gold will update with which suicide risk details | Clinical A-025 Identifying and Assessing Patients at Risk of Suicide-Self-Harm PandP PENDING |  |  | Paul Rains
| Emergency Services - Standard of Practice | Standards of practice | 1 | Yes | Jason Mihos & Sherry Brennaman |  | ASAP | ED nursing | No | See details. Questions about next steps (ED SoP updates needed?) -- will confirm with Tiffany | CSH Emergency Department Nursing Standards of Practice -FInal.docx
| Bladder Management | Policy | 1 | No | Trudy Finch |  | Clin Doc / Orders | Provider/Nursing | Yes | Ensuring the Indications from policy are in Gold | Bladder Management Policy.pdf https://commonspirit-national.policystat.com/policy/13986669/latest#autoid-rdymk |  | EHR Content | Rebecca Leach | Nursing-Missing 'Reason for Continuing IUC" = Epidural in Place. Policy does not recognize "Provider Managed" as a reason to continue. Nurse is able to place an IUC without a LIP Order. Not a clear place to document alternative management strategies attempted. Provider-The order for Urinary Catheter does not have any required 'Criteria for Use' documentation requirements.
| Perioperative - Standard of Practice |  | 1 |  | Kim Wilis |  |  | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice 4. Perioperative Nursing Standards of Practice (Preop, Intraop, Postop) Final
| ICU Liberation | Guideline | 1 | Yes | Marisa Radick |  | Clin Doc / Orders | Critical Care | Yes | Ensuring elements of the A-F bundle are built in Gold | CSH ICU Liberation ABCDEF Bundle Clinical Guidelines -Update Draft 2024).docx | Intake Slide ALM 4139 |  | Brenda Downs | See tab for missing elements of bundle Met with clin doc analysts on 2/11 to review needed build changes
| Valuables and Belongings | Policy | 1 | No | Melissa Plummer |  | Clin Doc | Nursing | Yes | Discharge for ED and for IP missing itemized list of pt belongings. Standardized Essential belongings not in Periop. - SEE Valuables & Belongings Tab | Template On Hold for V&B
| DAST-10 tool |  | 1 | No | Melissa Plummer |  | Clin Doc | BHU/Nursing/Stork | Yes | Not in Epic Gold SEE Dast-10 Tab | No National Policy or Guideline
| Perinatal - Standad of Practice |  | 1 | No | Melissa Plummer & Robin DeLorenzo |  |  | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice |  |  |  | Attached link does direct to site for SOP, however when clicking on Perinatal, the user is directed to WICI Institute page, which does not include SOP. VMMC does not have OB dept. Primary care may offer OB/GYN services, but patients are sent to FHS or another facility for delivery.
| Telemetry | Policy | 1 |  | Nicole Johnson |  | Clin Doc / Orders | Provider/Nursing | Yes
Yes | Vascular Access | Policy | 1 | Yes | Robin DeLorenzo |  | Clin Doc / Orders | Provider/Nursing | No |  | Clinical A-012 Vascular Access Selection, Adult POLICY w-Att 072722.pdf |  |  |  | There is a DMND that is in progress to match the policy
| Extravasavation Tx | Policy | 1 | Yes | Robin DeLorenzo |  | Clin Doc / Orders | Provider/Nursing | Yes | [5 empty] | A DMND is in progress to update the interventions per policy
| AMPAC Tool | Documentation | 1 | Yes | Robin DeLorenzo |  | Therapies OT,PT, SLP | Therapy | No | a documentation tool in Flowsheets needs licensure not approved |  |  |  |  | This is present in GOLD TST under therapy login
| Pediatric - Standards of Practice |  | 1 | No | Robin DeLorenzo & Melissa Plummer |  |  | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice |  |  |  | VMMC does not currently have a PEDs dept. There are clinics but the SOP is specific to IP.
| Details Will require multiple modules (ASAP, Interventional Radiology, Lumens, all Procedural areas). 5-10 hours of updates for each impacted team. Will require update to procedral narrators and Sedation Narrator | Policy | 1 | No | Sherry Brennaman |  | Clin Doc | Provider/Nursing | Yes | Details Will require multiple modules (ASAP, Interventional Radiology, Lumens, all Procedural areas) | Moderate and Deep Sedation SCI Workbook
| Point Click Care (State of Washington-EDIE (ED Information Exchange for WA State) | Epic Best Practice | 1 | Yes | Sherry Brennaman |  | Clin Doc / Orders / Willow | Provider/Nursing/Pharmacy | Yes | Care Coordination is requesting to be included in this work
| HAPI | Policy | 1 | Yes | Trudy Finch |  | Clin Doc / Orders | Provider/Nursing | Yes |  | Facility Template Policy - Hospital Acquired Pressure Injury (HAPI) Management EDITED.pdf |  | https://drive.google.com/drive/folders/1JlJahX8YcyVko8eoEKoS0iyyDbiPq_g3?usp=drive_link
| Chemo Policy | Policy | 1 | Yes | Trudy Finch |  | Oncology | Oncology | No | Work with Yvette | Antineoplastic -Chemotherapy - Immunotherapy- Prescribing and Administration for Oncology Indications POLICY- Clinical A-027.pdf | Antineoplastic -Chemotherapy - Immunotherapy- Prescribing and Administration for Oncology Indications PROCEDURE- Clinical A-027P.pdf
Yes | Vesicants | Policy | 1 | Yes | Van Nguyen |  | Clin Doc / Orders / Willow | Provider/Nursing/Pharmacy | Yes with Extravasation | vesicant meds identifed on the MAR | Alpha--Vesicant List Extravasation - Management and Treatment Guidance.docx
| Oncology Flowsheet | CAT Decisions | 1 | Yes | Yvette Kirk |  | Oncology |  | Yes | Chemo Admin |  |  |  | Lise/Marcia | Submitted viaTask Force
| CMU Virtual Telemetry - GE Carescape/Ascom | Project | 2 |  | Brooke Snow |  | Clin Doc / Orders | Provider/Nursing | Yes | Virtual Telemetry units monitored from CareBase in AZ | Project number: 1014176_0011081 |  |  | Gail Daily
| Virtually Integrated Care | Best Practice | 2 |  | Brooke Snow |  | Clin Doc / Orders | Provider/Nursing | Yes | Security Set up to identify virtual nurses
| SDOH | Guidelines | 2 | No | Marty Koepke |  | Clin Doc | Patient Care Services | Yes | Missing OPA for SW when safety responses are positive. |  |  |  |  | "For Non Harm questions > when Pt responds YES that they want a community, we need an OPA > Referral to SW. Community resource link needs to be available in Social Drivers to support WFs adding community resources to After Visit Summary. When SDOH driver responses score high enough across any/all domains an OPA fires for referral to SW. Should we adopt this for Gold? Previous Decision made? "
| Sepsis Protocol | Guideline | 2 |  | Marisa Radick |  | Clin Doc / Orders | Provider/Nursing | Yes |  | https://commonspirit-national.policystat.com/policy/18612396/latest#autoid-z4rar |  |  | Brenda Downs
| Preferred Language | Policy | 2 | Yes | Marisa Radick |  | Nursing | Patient Care Services | No | Ensuring the threshold languages are built in Gold |  |  |  | Lisa Macri | See tab for missing languages
| Critical Care - Standard of Practice |  | 2 |  | Marisa Radick & Brooke Snow |  |  | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice CommonSpirit Critical Care Nursing Standards of Practice Final-Approved Header.docx
| RT Pulmonary Mechanics | Requested by System Leader | 2 |  | Marty Koepke |  | Clin Doc | RT | Yes? | Work with Gold Analysts and System leaders for details
| Drug Screen Order for OB | Ticket # | 2 |  | Melissa |  | Stork | OB | Yes |  |  |  |  | Mindy Foster | Submitted viaTask Force
| Admit to NICU- precheck Vitamin K | Ticket # | 2 |  | Melissa |  | Stork | NICU | No | From SCOPE - Talk Diedre about details |  | Mountain Admit to Neonatal ICU order set updates
| National Numbers on AVS | Requested by System Individual | 2 |  | Melissa Plummer |  | Clin Doc | Nursing | No | List of standard national numbers needed on AVS | National Hotline Numbers- Epic Gold |  |  | Holly Gibbs/ Connie | Submitted viaTask Force-Check what is built, f/u with Tiff
| Outpatient in a bed | Requested by System VP Care Coordination | 2 |  | Melissa Plummer |  | Clin Doc | Care Coordination/Provider | Yes | Single order for outpatient in a bed | Copy of OIB Guidance - Final.docx |  |  | Gail Moxley | Submitted viaTask Force-does it match current updates to guideline?
| OralKleen (Comprehensive Oral Care) | Policy | 2 | No | Sherry Brennaman |  | Clin Doc | Nursing | No | Missing 2 options in Oral Care respose. Being updated for Wave 3. | Comprehensive Oral Care SCI Workbook
| Antimicrobial Prophylaxis Guidelines | Guidelines | 2 | No | Van |  | Willow / Orders | Pharmacy | No
| REMS Medications and Denials |  | 2 | No | Van |  | Willow | Pharmacy | No | this was not approved to be built in any envionrment yet. not in MTN in current state so not slated for GOLD. DMND0007976 is assigned 4- low priority at this time
| Quality Reporting |  | 2 |  | Team |  |  | Quality | No | Top 25 Quality Reports | Quality Priority Reporting Build Review-Epic Gold New Instance |  |  | Tracy Sklarr | Due on February 6, 2026
| Epic Denial Work Queue | Ticket # | 3 |  | Marisa Radick |  | Grand Central/ Prelude? | Rev Cycle |  |  |  | Epic Denial Work Queue Intake Slides |  | Diane Pirak
| HAPI RT Devices | System Request | N/A |  | Marty Koepke |  | Clin Doc | RT | No | Awaiting Final Design for Epic | [6 empty] | Epic Gold -> | Drive
| Harm to Others Policy | Policy | N/A |  |  |  | Clin Doc | BHU/Nursing | Yes | Awaiting Final Design - Let's make sure |  |  |  | Paul Rains | Design Not Complete

## References
Testing | Resources | Test Scripts (If Applicable)
CSH Policy/Published Guidelines | https://commonspirit-national.policystat.com/
CSH Standards of Practice | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice
Core Nursing SOP | CommonSpirit Core Nursing Standards of Practice.docx
O&M Promised for Gold
High Risk and Problematic Workflows such as: Medication Reconciliation, Blood Transfusion, DM Management etc.
Most Common Workflows such as: Admissions, Transfers, Discharges
Meet with Epic Gold Analysts that did the build | Clin Doc Team