## Info
Epic Gold System Policy Analysis and Action Plan
Purpose: This workflow aims to enhance collaboration between System Clinical Informaticists (SCI) and Application Analysts to accurately identify, prioritize, and remediate missing System Policy components within Epic Gold. The goal is to ensure the current build precisely mirrors the requirements outlined in CSH policy, fostering data integrity and operational efficiency.
Target Audience: SCI, SCI Managers, Application Analyst Managers, and Application Analysts
Please DO NOT edit formulas without SCI involvement
Workflow Steps:
1. CI Identification of Missing Component(s)
SCI review CSH policy to Epic Gold build and identify discrepancies related to existing System Policy requirements
2. SCI Manager Priority Assessment
The SCI Manager review and prioritize each missing component
3. Analyst Manager Assignment
The Application Analyst Manager assigns each task to the appropriate Primary Application Analyst
4. Primary Analyst & SCI Collaboration
The assigned Primary Analyst and Primary SCI collaborate closely to define the detailed build requirements and scope. Involving: Establishing meeting cadence (collaborative calls, email, etc.) for efficient collaboration for all participants Identifying Epic records that need to be created, modified, or removed Evaluate potential downstream impacts of requested changes Engaging other module analysts as needed Involving key stakeholders if further decisions are required (SCI) Identifying if end-user education is required with the change
5. Analyst and SCI Tracking and Progress
Accurately document status, milestones, roadblocks, and escalations within the Master Missing Components Log The Primary Analyst is responsible for tracking the build progress of their assigned tasks within their individual spreadsheet The SCI is responsible for tracking information on the Master Missing Components Log and any decisions pertaining to the required build Note: Update any Orion tasks associated with the build if applicable
6. Weekly Updates for Management
Before end of day Friday, update tracker with any relevant data related to the task

## InitiativeDocuments
id | initiativeId | documentName | documentType | url | dateAdded
IDC-0001 | EG-0003 | Candida auris Design Sheet for Legacy Epic Sites | Design Spec | https://docs.google.com/spreadsheets/d/1_51LtrQZBNRNAXjOkPEUAFo_XOEnJiE1bBY7RP6Mu2I/edit?gid=756037640#gid=756037640 | 2026-03-12T13:43:12.939Z
IDC-0002 | EG-0003 | Candida auris Testing Script | Test Plan | https://docs.google.com/spreadsheets/d/11xeOnI4MvqZWBeyHwUHPO0V6PJW1OAH0epxw5sF7T8I/edit?gid=1512032825#gid=1512032825 | 2026-03-12T13:43:45.661Z
IDC-0003 | EG-0017 | Patient Personal Belongings and Valuables | Policy | https://docs.google.com/document/d/1cIXT8O4rCkUSWTiFjNc8FwxB5HJD_Mir/edit | 2026-03-12T15:59:16.122Z
IDC-0004 | EG-0010 | Bladder Management Protocol | Policy | https://drive.google.com/file/d/1_TUHzUthrujj4k4Z_F39AHOBU7vbRsSL/view?usp=sharing | 2026-03-16T18:40:52.052Z
IDC-0005 | EG-0002 | Missing Components for Nursing SOP | Requirements | https://docs.google.com/spreadsheets/d/1v1GiS8A9rd1Bn6qhk_jFNEuQDSS8BCtBWEPe4IChoNU/edit?gid=0#gid=0 | 2026-03-16T19:29:49.047Z
IDC-0006 | EG-0004 | Nurisng SOP Missing Components | Requirements | https://docs.google.com/spreadsheets/d/1v1GiS8A9rd1Bn6qhk_jFNEuQDSS8BCtBWEPe4IChoNU/edit?gid=0#gid=0 | 2026-03-16T19:30:37.467Z
IDC-0007 | EG-0006 | Nursing SOP Missing Components | Requirements | https://docs.google.com/spreadsheets/d/1v1GiS8A9rd1Bn6qhk_jFNEuQDSS8BCtBWEPe4IChoNU/edit?gid=0#gid=0 | 2026-03-16T19:31:06.453Z
IDC-0008 | EG-0007 | Nursing SOP Missing Components | Requirements | https://docs.google.com/spreadsheets/d/1v1GiS8A9rd1Bn6qhk_jFNEuQDSS8BCtBWEPe4IChoNU/edit?gid=0#gid=0 | 2026-03-16T19:31:35.739Z
IDC-0009 | EG-0012 | Nursing SOP Missing Components | Requirements | https://docs.google.com/spreadsheets/d/1v1GiS8A9rd1Bn6qhk_jFNEuQDSS8BCtBWEPe4IChoNU/edit?gid=0#gid=0 | 2026-03-16T19:32:32.014Z
IDC-0010 | EG-0010 | TSK-0039 Order Changes | Build Guide | https://docs.google.com/document/d/1f7s_a6KhZWEx07rXdxm5YLC0l9YMGHwm-KeqG34ZNjQ/edit?tab=t.0 | 2026-03-16T19:58:22.685Z
IDC-0011 | EG-0026 | Design Updates For Gold | Build Guide | https://docs.google.com/spreadsheets/d/1fbwBgPteaPWnmdkzz1-2J4JA0878oRDj3cv_7-5XKrE/edit?gid=0#gid=0 | 2026-03-16T20:41:54.902Z
IDC-0012 | EG-0011 | SDOH Review in Gold | Other | https://docs.google.com/spreadsheets/d/1xlCAceRaIOrdlvS8BXvgpbTdxiNPqhFD3UyFN5A0cV8/edit?gid=58930183#gid=58930183 | 2026-03-17T16:14:10.385Z
IDC-0013 | EG-0019 | Depression Testing and Outcomes | Other | https://docs.google.com/document/d/19hOO9rOmzFjQs6ZVSfKglJFpMM6BXQ00r86oSnNKCkI/edit?usp=sharing | 2026-03-17T16:16:26.532Z
IDC-0014 | EG-0011 | CSH National SDOH Define Standards | Requirements | https://docs.google.com/presentation/d/1_JlJ5zEueI2YDZOuxt2yNFqyCgO4_w5zKN4MITRfbfc/edit?slide=id.geaa92738cc_0_0#slide=id.geaa92738cc_0_0 | 2026-03-17T16:44:59.727Z
IDC-0015 | EG-0017 | Gold Build Review Check Off - Valuables and Belongings | Other | https://docs.google.com/spreadsheets/d/1rq45ZkY7pWVoRcEFE0vR8oMQjAMAdJp-CIVyNCIIvNk/edit?gid=130875306#gid=130875306 | 2026-03-17T17:03:47.625Z
IDC-0016 | EG-0027 | Policy / Guideline | Policy | Comprehensive Oral Care SCI Workbook | 2026-03-17T19:22:21.808Z

## Initiatives
id | name | description | type | priority | primarySCI | secondarySCI | applications | venues | rolesImpacted | specialtyServiceLine | systemSponsor | goLiveWave | policyLink | ehrRequirementsLink | status | createdDate | updatedDate
EG-0002 | Nursing Travel Screening Assessment | Need Foundation Travel Screening within Admission Navigator and Required Documentation | Standard Practice | High | Brooke Searl | Marisa Radick | Clindoc | Acute Inpatient | Nursing |  | Alison Mason | Wave 3 |  |  | In Progress | 2026-03-11T20:52:08.868Z | 2026-03-18T16:34:59.051Z
EG-0003 | Candida auris | System guideline to aid in the indentification C. auris patients coming from high risk facilities | Guideline | High | Brooke Searl | Marisa Radick | ClinDoc,OPA,Bugsy | Acute Inpatient,ED | Nursing,Provider,Infection Prevention |  | Becky Leach | Wave 3 |  |  | Ready for Discussion | 2026-03-11T20:52:08.868Z | 2026-03-18T16:36:49.047Z
EG-0004 | Nursing Head to Toe Assessment | Basic assessment flowsheet is missing rows related to the neurology and cardiac assessments | Standard Practice | High | Brooke Searl | Marisa Radick | Clindoc |  |  |  | Alison Mason | Wave 3 |  |  | Under Review | 2026-03-11T20:52:08.868Z | 2026-03-18T16:37:19.373Z
EG-0006 | Nursing Fall Assessment | Can only document interventions on the Screenings Flowsheets, not within the Daily Cares Flowsheet | Policy | High | Brooke Searl | Marisa Radick | Clindoc |  |  |  | Alison Mason | Wave 3 |  |  | Under Review | 2026-03-11T20:52:08.868Z | 2026-03-17T20:28:33.768Z
EG-0007 | Nursing Skin Assessment | an only document interventions with the Braden, not the BradenQ | Standard Practice | High | Brooke Searl | Marisa Radick | Clindoc | Acute Inpatient | Nursing |  | Alison Mason | Wave 3 |  |  | Under Review | 2026-03-11T20:52:08.868Z | 2026-03-17T20:28:59.545Z
EG-0008 | Suicide risk policy | Ensure clinical dashboards include suicide risk elements per recent Epic updates | Policy | Medium | Jason Mihos |  | Clindoc | Acute Inpatient,ED |  |  |  | Wave 3 |  |  | In Progress | 2026-03-11T20:52:08.868Z | 2026-03-17T19:39:09.809Z
EG-0009 | ED Abuse, Neglect, Violence Screening | Need to ensure that complete screening documentation resources are appropriately available. | Standard Practice | High | Jason Mihos |  | Clindoc,ASAP | ED |  |  |  | Wave 3 |  |  | Under Review | 2026-03-11T20:52:08.868Z | 2026-03-17T20:01:01.406Z
EG-0010 | Bladder Management | Need to ensure indications, orders and other documentation are correct. | Standard Practice | High | Trudy Finch | Sherry Brennaman | Clindoc,Orders | Acute Inpatient | Nursing |  |  | Wave 3 |  |  | In Progress | 2026-03-11T20:52:08.868Z | 2026-03-17T19:53:26.544Z
EG-0011 | SDOH (Acute, ED, Amb, HOD) | SDOH needs standard implementation across storyboard, flowsheets, OPAs, AVS. Includes the addition of nursing intervention documentation for positive IPV responses. | Guideline | High | Marty Koepke | Melissa Plummer | ClinDoc | ED,Acute Inpatient,Ambulatory | Provider,Nursing,Medical Assistants,Care Coordination,Social Work |  | Ankita Sagar | Wave 3 |  |  | Ready for Discussion | 2026-03-11T20:52:08.868Z | 2026-03-17T21:07:18.563Z
EG-0012 | Nursing SOP - Dialysis Graft/Fistula | AV Fistula and AV Graft LDAs require need additional selections. | Standard Practice | Medium | Brooke Searl | Marisa Radick | Clindoc | Acute Inpatient | Nursing,Provider |  | Alison Mason | Wave 3 |  |  | Under Review | 2026-03-11T20:52:08.868Z | 2026-03-18T16:37:41.713Z
EG-0013 | Sedation Policy Narrator | Several items need to be reviewed, added or corrected | Standard Practice | Medium | Sherry Brennaman |  | Clindoc,ASAP,Rad,Lumens,Optime | Periop | Nursing |  |  | New Beginnings South |  |  | Not Started | 2026-03-11T20:52:08.868Z | 2026-03-17T16:46:53.895Z
EG-0015 | Preferred Languages |  | Standard Practice | Medium | Marisa Radick |  | Grand Central | ED,Acute Inpatient,Ambulatory,Periop,Outpatient Surgery,Acute Outpatient |  |  |  | Wave 3 |  |  | Ready for Discussion | 2026-03-11T20:52:08.868Z | 2026-03-17T21:58:31.632Z
EG-0016 | ICU Liberation | Missing components from the ICU Liberation Bundle | Guideline | Medium | Marisa Radick | Brooke Searl | Clindoc | Acute Inpatient | Nursing |  | Brenda Downs | Wave 3 |  |  | Completed | 2026-03-11T20:52:08.868Z | 2026-03-17T16:30:08.885Z
EG-0017 | Valubles & Belongings | Does align with policy. Screenshots in documents attached to task | Policy | Medium | Melissa Plummer |  | Clindoc,ASAP,OpTime |  |  |  |  | Wave 3 |  |  | In Progress | 2026-03-11T20:52:08.868Z | 2026-03-17T17:07:55.622Z
EG-0018 | DAST10 | DAST 10 needs to be appropriately placed for documentation and results findings | Guideline | Medium | Melissa Plummer |  | Stork | Acute Inpatient,ED | Nursing,Provider,Care Coordination,Social Work |  |  | New Beginnings South |  |  | In Progress | 2026-03-11T20:52:08.868Z | 2026-03-17T17:12:48.365Z
EG-0019 | Amb: Depression Screening (PHQ2/9/A) | Need to ensure all elements are correctly included for adults and teens | Standard Practice | High | Marty Koepke |  |  | Ambulatory | Medical Assistants,Provider |  | Deb Rockman | Wave 3 |  |  | Ready for Discussion | 2026-03-11T22:14:21.112Z | 2026-03-17T21:08:52.885Z
EG-0020 | Amb: BP - 2nd Reading for 140/90 | Discovery needed. System guideline indicates we need a 2nd BP reading for BP 140/90+. We see red for awareness, but no downstream alerting to retake a 2nd pressure during the amb encounter. | Guideline | High | Marty Koepke |  | Ambulatory | Ambulatory | Provider,Medical Assistants |  | Deb Rockman | Wave 3 |  |  | Ready for Discussion | 2026-03-11T22:17:32.236Z | 2026-03-17T21:09:47.627Z
EG-0022 | Amb: Medicare Annual Wellness | Need to confirm MyChart expected behavior | Standard Practice | High | Marty Koepke |  | Ambulatory | Ambulatory | Medical Assistants,Provider |  | Deb Rockman | Wave 3 |  |  | Ready for Discussion | 2026-03-12T00:42:55.137Z | 2026-03-17T21:10:09.909Z
EG-0023 | Age Friendly Documentation | More information is needed by Dawn to complete readiness for this item. | Board Goal | High | Dawn Jacobson |  | Clindoc |  |  |  |  | New Beginnings South |  |  | Under Review | 2026-03-13T19:29:20.360Z | 2026-03-17T22:21:58.314Z
EG-0024 | Restraints | Components required to meet CMS standards for restraint documentation. | Standard Practice | High | Brooke Searl | Marisa Radick | ClinDoc | Acute Inpatient | Nursing |  | Kerri Culver | Wave 3 |  |  | Under Review | 2026-03-16T17:11:38.264Z | 2026-03-18T16:38:15.299Z
EG-0025 | Extravasation FLT Documentation | CSH policy requires extravasation documentation to be completed q 1 hour x 2 then at least q 4 hours post extravasation recognition. No documentation available for extravasation tracking in Gold. Can document Phelbitis and Infiltration within the LDA but, the LDA documentation does not support documentation after removal of the line. | Policy | Medium | Brooke Searl | Marisa Radick | ClinDoc | Acute Inpatient | Nursing |  | Lauren Bulin | Wave 3 |  |  | In Progress | 2026-03-16T19:26:50.746Z | 2026-03-16T19:26:50.746Z
EG-0026 | Interpreter Service Documentation | Interpreter services documentation needs to align with new policy standards | Policy | High | Marty Koepke | Melissa Plummer |  | ED,Acute Inpatient,Ambulatory,Periop,Acute Outpatient,Outpatient Surgery | Registration/Front Office,Nursing,Medical Assistants |  | Connie Clemmons Brown/ Lisa Macri | Wave 3 |  |  | Ready for Discussion | 2026-03-16T20:40:58.812Z | 2026-03-17T21:05:12.833Z
EG-0027 | OralKleen (Comprehensive Oral Care) | Update Responses for Oral Care - Alex already built in NonProd | Policy | Medium | Sherry Brennaman |  | Clin Doc | Acute Inpatient | Nursing,Respiratory/Rehab,Infection Prevention |  |  | Wave 3 |  |  | In Progress | 2026-03-17T19:22:20.654Z | 2026-03-17T19:34:36.326Z

## Tasks
id | initiativeId | description | module | priority | primaryAnalyst | additionalAnalysts | status | educationRequired | buildReviewComplete | buildReviewDate | resolutionDate | createdDate
TSK-0005 | EG-0002 | Add in Foundation Travel screening to all admission navigators - FS Travel screening already aligns with Legacy Epic workflows | ClinDoc | High | Alex Cordell |  | Build In Progress | No | In Progress | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0006 | EG-0003 | Provider OPA: An interruptive OPA when a high risk patient is admitted. | OPA | High | Michelle Ryan |  | Identified | No | In Progress | 2026-03-18 |  | 2026-03-11T20:52:08.868Z
TSK-0007 | EG-0004 | Neuro: Include LOC, Orientation Status, Facial symmetry, Speech, Cental nerves (corneal, cough, gag), DTR | ClinDoc | High | Alex Cordell |  | Analyst Assigned | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0009 | EG-0006 | Add flowsheet rows for Fall Interventions in the Daily Cares flowsheet | ClinDoc | High | Alex Cordell |  | Identified | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0010 | EG-0007 | Add Intervention documentation to the BradenQ. | ClinDoc | High |  |  | Identified | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0012 | EG-0009 | Missing Fields: Abuse/neglect, violence screening -- neglect not included | ASAP | High | Megan Rutt |  | Analyst Assigned | No | In Progress | 2026-03-17 |  | 2026-03-11T20:52:08.868Z
TSK-0013 | EG-0010 | Missing Fields: Indications missing Epidural in Place,. | ClinDoc | High | Christi Allen |  | Identified | No | In Progress | 2026-03-17 |  | 2026-03-11T20:52:08.868Z
TSK-0015 | EG-0011 | CMS AHS core Social Drivers questions as well as Nursing Interventions need to be available in relevant flowsheets. Observation of harm question and nursing intervention questions need to be clearly labeled as RN only. The desire is to leverage same flowsheet ID for all areas, if possible. |  | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T20:52:08.868Z
TSK-0016 | EG-0011 | OPA needs for referral to SW on + IPV responses (Acute and ED) | OPA | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T20:52:08.868Z
TSK-0017 | EG-0011 | OPA for SW when patient responds to desiring assistance to non safety questions. (ED/Acute) | OPA | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T20:52:08.868Z
TSK-0018 | EG-0012 | AV Fistula can only select one option for Thrill, bruit, Absent, Present - Should this be multi-select | ClinDoc | High | Corrinne Welch |  | Build Analyst Assigned | No | In Progress | 2026-02-11 |  | 2026-03-11T20:52:08.868Z
TSK-0019 | EG-0013 | Will need to be broken down into into appropriate individual tasks: Missing Fields: Vital Signs - Missing ECO2 Waveform Pre-Procedure Checklist (ED) Rad Studies Available? Beta Blocker VTE Prophylaxis Normothermia Measures Stop Bang Sign In / Briefing - Missing Time Out Sign Out or Debriefing - Missing ¦ Analyst/SCI Initial Build Review Complete: No - Did not meet with analyst) | ASAP | High | Adam Henderson |  | Identified | Yes | No - Did not meet with analyst |  |  | 2026-03-11T20:52:08.868Z
TSK-0021 | EG-0015 | Missing Languages: Persian Navajo Slightly Different Spelling: Punjabi (Spelled Panjabi) Urdu (Written as Urdu Pakistan) ¦ Analyst/SCI Initial Build Review Complete: No - Did not meet with analyst) | Grand Central | Medium | Desiree Upton |  | Identified | No | In Progress |  |  | 2026-03-11T20:52:08.868Z
TSK-0022 | EG-0016 | SAT Safety Screen SBT Safety Screen Early Progressive Mobility Protocol: Screen for Safety Daytime/Nightime Interventions - does this need to be documented in EHR? | ClinDoc | Medium | Sara Garcia |  | Closed - Completed | No | Yes - Build can be complete | 2026-02-11 | 2026-03-12 | 2026-03-11T20:52:08.868Z
TSK-0023 | EG-0017 | Policy Screenshots provided | ClinDoc | High | Alex Cordell |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-11T20:52:08.868Z
TSK-0024 | EG-0018 | The DAST-10 tool is only found when searching the Database in Flowsheets | Stork | Medium |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-11T20:52:08.868Z
TSK-0025 | EG-0011 | OPA design needed for positive IPV responses, to provider on that visit encounter, to inform provider of + responses |  | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T21:10:29.521Z
TSK-0026 | EG-0011 | OPA needed to remind MAs to provide community referral when patient responds yes to wanting assistance on non harm questions. | OPA | High |  |  | Identified | Yes | In Progress | 2026-03-10 |  | 2026-03-11T21:11:30.645Z
TSK-0027 | EG-0011 | After Visit Summary alignment to provide link to Find Help (add URL), on AVS where SDOH screenings are performed. (ED, Acute, Amb, HODs) |  | High |  |  | Identified | No | In Progress | 2026-03-10 |  | 2026-03-11T21:12:46.470Z
TSK-0028 | EG-0004 | Cardiac: Update Cardiac Symptoms to include chest pain, Update Chest Tubes LDA for patency, Include Implantable Cardiac Defibrillators rows | ClinDoc | High | Alex Cordell |  | Identified | No | Yes - Build can be complete | 2026-02-11 |  | 2026-03-11T21:26:54.456Z
TSK-0029 | EG-0012 | AV Graft needs the option to document Thrill, bruit, Absent, Present | ClinDoc | High |  |  | Build Analyst Assigned | No | In Progress | 2026-02-11 |  | 2026-03-11T21:36:09.731Z
TSK-0030 | EG-0003 | IP and Nursing OPA: A Storyboard OPA when a high risk patient is admitted. | OPA | Medium | Michelle Ryan |  | Identified | No | In Progress | 2026-03-18 |  | 2026-03-11T21:41:27.915Z
TSK-0031 | EG-0020 | PHQA needs OPA when score is >4 | OPA | High |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-11T22:23:38.949Z
TSK-0032 | EG-0019 | OPA needed for positive PHQA for provider to do an interpretation and follow up plan if needed | OPA | High |  |  | Identified | Yes | No - Did not meet with analyst |  |  | 2026-03-11T22:36:24.845Z
TSK-0033 | EG-0022 | Needs review and confirmation of current behavior: observed that for MyChart high depression score a message is sent to the provider. What are the rules around depression screening results provided via portal? |  | High |  |  | Identified |  | No - Did not meet with analyst |  |  | 2026-03-12T00:44:48.118Z
TSK-0034 | EG-0019 | Results of PHQ2/9/A need to auto populate note templates for Amb Office Visits |  | High |  |  | Identified |  | No - Did not meet with analyst |  |  | 2026-03-12T00:46:08.858Z
TSK-0035 | EG-0019 | Needs Clarification: For negative depression screenings. Score = 0, does a G code automatically drop for these? If not, what is workflow expectation |  | High |  |  | Identified |  | No - Did not meet with analyst |  |  | 2026-03-12T00:47:20.491Z
TSK-0036 | EG-0003 | Add infection status of Rule Out Candida auris | Bugsy | Medium | Jennifer Brennan |  | Build Analyst Assigned | No | In Progress | 2026-03-18 |  | 2026-03-12T13:44:37.373Z
TSK-0037 | EG-0010 | Nurse is able to place an IUC without a LIP Order. | Orders | Medium |  |  | Dismissed | No | No - Did not meet with analyst |  |  | 2026-03-12T15:45:17.228Z
TSK-0038 | EG-0010 | Not a clear place to document alternative management strategies attempted | ClinDoc | Medium | Christi Allen |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-12T15:45:50.562Z
TSK-0039 | EG-0010 | Order for Urinary Catheter does not have any required 'Criteria for Use' documentation requirements | Orders | High | Jared Boynton |  | Identified | No | In Progress | 2026-03-17 |  | 2026-03-12T15:46:31.558Z
TSK-0040 | EG-0008 | Updated suicide risk elements represented in the following dashboards: ED key metrics OB nurse manager Inpt quality nurse |  | Medium |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-12T15:47:48.647Z
TSK-0041 | EG-0018 | Provider Notification also does not display and is only found in the Database when looking for Flowsheets | Stork | Medium |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-12T16:02:50.598Z
TSK-0042 | EG-0018 | Neither of the options when displayed in Flowsheets contains the Interventions as seen in FHS and CEN | Stork | Medium |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-12T16:03:14.227Z
TSK-0043 | EG-0003 | Candida auris PCR Order needs option to have axilla swab | Orders | Medium |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-13T17:55:42.665Z
TSK-0044 | EG-0024 | Geri Chair only in NV Violent Restraint FLT - Remove Geri Chair and add Restraint Chair for Violent | ClinDoc | High |  |  | Identified | Yes | No - Did not meet with analyst |  |  | 2026-03-16T19:24:34.071Z
TSK-0045 | EG-0025 | Add FLT, T CHI IP Extravasation [511], into Epic Gold to support VAS policy for extravasation documentation | ClinDoc | Medium |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-16T19:27:42.353Z
TSK-0046 | EG-0024 | Within NV FLT Restraint Monitoring group add rows: Physical Comfort Observation status rows | ClinDoc | High |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-16T19:35:40.904Z
TSK-0047 | EG-0024 | Violent Restraints FLT, after Restraint Order Group add Security called Group from FS | ClinDoc | High |  |  | Identified |  |  |  |  | 2026-03-16T19:36:51.176Z
TSK-0048 | EG-0024 | Violent - remove the word waist, update to Hip | ClinDoc | High |  |  | Identified |  |  |  |  | 2026-03-16T19:37:19.024Z
TSK-0049 | EG-0024 | Add Leadership group from CEN after Debreifing | ClinDoc | High |  |  | Identified |  |  |  |  | 2026-03-16T19:37:56.601Z
TSK-0050 | EG-0024 | Violent: Face to Face (Within 1H) drop down required, use CEN FLT row, Tiff to send over requirement needs for F2F from Joint Commission | ClinDoc | High |  |  | Identified |  |  |  |  | 2026-03-16T19:38:54.088Z
TSK-0051 | EG-0026 | Field updates needed for Navigator view ED/Acute/Amb (see attached document) | ClinDoc | High |  |  | Identified | Yes | No - Did not meet with analyst |  |  | 2026-03-16T20:43:53.831Z
TSK-0053 | EG-0026 | CSH performance metrics needed (see attached document) |  | High |  |  | Identified | No | No - Did not meet with analyst |  |  | 2026-03-16T20:45:43.917Z
TSK-0054 | EG-0023 | Load Turbocharger package for Age Friendly content |  | High |  |  | Identified |  |  |  |  | 2026-03-17T14:12:53.059Z
TSK-0055 | EG-0023 | Create expanded SDOH section-age based criteria (equal to or greater than 65 years); Social isolation, caregiver stress and financial abuse questions |  | Medium |  |  | Identified |  |  |  |  | 2026-03-17T14:14:48.994Z
TSK-0056 | EG-0023 | Creation of Age Friendly Section in Admission Navigator (age based criteria)-to include screening tools (CAM, PHQ) and pull Mobility screening information already documented in Admission Navigator (Morse and ADL); Interventions section are standard AF content conditional based on screening results |  | Medium |  |  | Identified |  |  |  |  | 2026-03-17T15:18:06.204Z
TSK-0058 | EG-0011 | SDOH in Navigator (Nursing, Provider) | ASAP | High |  |  | Identified | Yes | No - Did not meet with analyst |  |  | 2026-03-17T16:20:52.569Z
TSK-0060 | EG-0013 | Sedation Narrator Updates | ASAP | Medium | Adam Henderson |  | Identified | Yes |  |  |  | 2026-03-17T19:18:28.386Z
TSK-0061 | EG-0013 | Procedural Narrator Updares |  | Medium |  |  | Identified | Yes |  |  |  | 2026-03-17T19:19:05.109Z
TSK-0062 | EG-0013 | Flowsheet Row Updates | ClinDoc | Medium |  |  | Identified |  |  |  |  | 2026-03-17T19:19:44.204Z
TSK-0063 | EG-0027 | Updates to Oral Care Row to uclude Oral mucosal care Tongue Scraping | ClinDoc | High | Alex Cordell |  | Build In Progress | No |  |  |  | 2026-03-17T19:28:15.394Z

## Notes
id | taskId | initiativeId | timestamp | author | noteText | noteType
NTE-0002 | TSK-0032 |  | 2026-03-12T00:39:32.623Z | marty.koepke@commonspirit.org | Email sent to Kelly Bitonio | Status Update
NTE-0003 | TSK-0022 |  | 2026-03-12T14:13:48.686Z | brooke.snow@commonspirit.org | Marisa sent two corrections back over to Sara on 2/26, awaiting her response to perform a final review | General
NTE-0004 | TSK-0043 |  | 2026-03-13T17:56:34.273Z | brooke.snow@commonspirit.org | Add a note on the progress of this ticket. I met the analyst and they will proceed with the build. | General
NTE-0005 | TSK-0022 |  | 2026-03-13T18:08:34.674Z | marisa.radick@commonspirit.org | Sara completed final changes, build can be marked as complete | General
NTE-0007 |  | EG-0023 | 2026-03-16T20:21:02.525Z | marty.koepke@commonspirit.org | Testing Notes | General
NTE-0008 |  | EG-0024 | 2026-03-16T20:24:39.906Z | brooke.snow@commonspirit.org | Met with Tiffany Lofgren (in place of Kerri Culver) and Salvacion Quimosing on Monday March 16th to review Epic Gold Restraint build. Request placed to update documentation per CMS guidelines. Assessing with Cyndi Meldon and Mary Kane if these requests need to go through CSH leadership for final approval before changes are made. | General
NTE-0009 | TSK-0055 |  | 2026-03-17T15:15:50.673Z | dawn.jacobson@commonspirit.org | Possible to be added to SDOH EG missing build | General
NTE-0010 |  | EG-0011 | 2026-03-17T16:48:16.985Z | marty.koepke@commonspirit.org | Per Jason M. It appears that Social Drivers is in ED/ASAP. Just want to confirm it is complete and aligns with standard | General
NTE-0011 | TSK-0023 |  | 2026-03-17T16:50:48.599Z | brooke.snow@commonspirit.org | Alex and Melissa working on validating the needed changes | General
NTE-0012 | TSK-0019 |  | 2026-03-17T16:52:16.884Z | brooke.snow@commonspirit.org | Need additional builders from Radiology, Procedural, Clindoc, etc. | General
NTE-0013 |  | EG-0018 | 2026-03-17T17:12:21.866Z | melissa.plummer@commonspirit.org | E-mail conversation with Maria Delacruz, Sheron Johnson, and Kate Glass re needs for the build. Kate has responded the build is in early phases and is not yet complete. She is aware of DAST-10 request and it will be included in Gold build. Available to view in TST2 in the SOU instance. | General
NTE-0014 |  | EG-0003 | 2026-03-17T17:18:41.375Z | brooke.snow@commonspirit.org | Brooke is meeting with OM and Gold analysts to review required build for Epic Gold on Wednesday, March 18th. | General
NTE-0015 | TSK-0021 |  | 2026-03-17T18:59:29.035Z | marisa.radick@commonspirit.org | Spoke to Desiree Upton, I missed that there was a Farsi/Persian selection, which will suffice. Following up with Lisa Macri to confirm if "Native American Indian" will suffice for Navajo or if we need a distinct option built out | General
NTE-0016 | TSK-0005 |  | 2026-03-17T19:15:38.072Z | alex.cordell@commonspirit.org | Need to add SEC_ED_TRAVEL_SCREENING to admission nursing navigators | General
NTE-0017 |  | EG-0027 | 2026-03-17T19:30:32.619Z | sherry.brennaman@commonspirit.org | As of 2/11/26 Alex has built this in POC. | Status Update
NTE-0018 | TSK-0007 |  | 2026-03-17T19:34:48.720Z | alex.cordell@commonspirit.org | We need to update the Basic Assessment Neuro section to match complex assessment | General
NTE-0019 | TSK-0028 |  | 2026-03-17T19:35:30.067Z | alex.cordell@commonspirit.org | Add "Chest Pain" to FLO 3040103171 R Cardiac Symptoms G Cardiac Simple needs ICD documentation - Brooke is clarifying how we want that to be made available (match basic assessment for tele or closer to complex with the additional assessment row) | General
NTE-0020 |  | EG-0008 | 2026-03-17T19:36:01.269Z | marty.koepke@commonspirit.org | Dashboard work is happening now. ASAP team doing the work | General
NTE-0021 | TSK-0009 |  | 2026-03-17T19:36:34.084Z | alex.cordell@commonspirit.org | Braden G SKIN BRADEN SCALE GROUP is broken and not hiding rows that should be cascading. Brooke will be getting more information regarding which fall group currently in TST needs to be leveraged. | General
NTE-0022 | TSK-0038 |  | 2026-03-17T19:52:31.752Z | marty.koepke@commonspirit.org | Nurse does non invasive interventions before catheter. This is a pre intervention to prevent placing a catheter. How is this documented today? Alternative to catheter field available to document. A flowsheet row. Possible Cerner design. We need to ID the verbiage and choice selections to determine appropriate flowsheet placement. | General
NTE-0023 |  | EG-0010 | 2026-03-17T20:44:24.213Z | christi.allen@commonspirit.org | sent email to Trudy with current custom list options, seeking clarification on exact language to use, as well as confirming which LDAs the row should include. CLA | General
NTE-0024 |  | EG-0026 | 2026-03-17T20:57:03.919Z | christi.allen@commonspirit.org | requested access to spreadsheet with requested changes CLA | General
NTE-0025 | TSK-0037 |  | 2026-03-17T21:28:14.661Z | trudy.finch@commonspirit.org | Dismissed, not an issue | General
NTE-0026 | TSK-0039 |  | 2026-03-17T21:31:46.704Z | trudy.finch@commonspirit.org | Meet with EPIC Orders Team on 3/17. Determine that two 'Indications' need to be changed in the UC order: acute urinary retention that cannot be managed using less-invasive methods Change Obstruction to: ‘Obstruction/Retention (urinary)’ assist in healing of open sacral or perineal wounds in incontinent patients Change Decubitus Ulcer to: ‘Sacral/Perineal wound(s)’ Challenges to getting these changes done my Wave 3 for Orders and Order Sets: EPIC Analyst team feels these changes need approval from Gold IT Leadership. All changes have been stopped except for: Patient safety issues Revenue impact Provider personalization labs have already started. Workload limitations Needs approval for the Clinical Approving Group that owns this policy, for the current build. | General
NTE-0027 | TSK-0010 |  | 2026-03-17T21:54:50.619Z | marty.koepke@commonspirit.org | Braden G SKIN BRADEN SCALE GROUP is broken and not hiding rows that should be cascading | General
NTE-0028 | TSK-0012 |  | 2026-03-17T21:55:15.539Z | marty.koepke@commonspirit.org | Address missing neglect documentation in ASAP | General
NTE-0029 | TSK-0027 |  | 2026-03-17T21:56:06.622Z | marty.koepke@commonspirit.org | Need to determine if a print group for this exists for acute IP Gold. | General
NTE-0030 | TSK-0016 |  | 2026-03-17T21:56:29.072Z | marty.koepke@commonspirit.org | Need best practice recommendation to alert providers that patient responded + to harm question, and/or are asking for support to non harm questions. Also to alert staff to create a community referral when patient is asking for support to non harm items. | General
NTE-0031 | TSK-0017 |  | 2026-03-17T21:56:47.424Z | marty.koepke@commonspirit.org | Need best practice recommendation to alert providers that patient responded + to harm question, and/or are asking for support to non harm questions. Also to alert staff to create a community referral when patient is asking for support to non harm items. | General
NTE-0032 | TSK-0015 |  | 2026-03-17T21:57:07.249Z | marty.koepke@commonspirit.org | """Needs design review. Core CMS questions + observation of abuse question + nursing intervention questions available for RNs Only. Easiest conceived design is to have a single flowsheet that has all elements, with clear RN Only headers for Observation and nursing intervention sections. Needs some review. Appears that correct Social Drivers screening flowsheet has not been applied appropriately across positions/venues. EDRN in Gold TST do not have the correct flowsheet applied to preference list. """ | General
NTE-0033 | TSK-0013 |  | 2026-03-17T22:24:00.064Z | trudy.finch@commonspirit.org | Emailed Christi Allen on 3/17 of ClinDoc Team: Update the following FLO Record ID 7085610 &7085670 with 'Epidural in Place'. | General
NTE-0034 | TSK-0005 |  | 2026-03-18T15:10:48.077Z | alex.cordell@commonspirit.org | This is now available in all nursing admission navigators except: MODEL_BH_RN_ADMISSION_TEMPLATE [1540000000] Reached out to Brooke to see if we need this added to our BH admission navigator as well | General
NTE-0035 |  | EG-0002 | 2026-03-18T16:18:29.261Z | brooke.snow@commonspirit.org | Add Travel Screening to BH Navigator | Decision
NTE-0036 |  | EG-0003 | 2026-03-18T16:22:01.687Z | brooke.snow@commonspirit.org | Met with Jennifer Brennan (bugsy Gold analyst) 3/18/26 to discuss required needs for build. Sent email to Becky Leach to see what expiration date needs to be set for R/O Candida auris infection status as these are all set at the patient level. Sent email to Michelle Ryan inquiring if the OPA build can be completed prior to Wave 3 Go live Waiting on response for Stephanie Carr for a Reporting analyst to help with the Gold build | General
NTE-0037 | TSK-0007 |  | 2026-03-18T16:22:58.410Z | brooke.snow@commonspirit.org | Set Basic Assessment, Neuro, to mirror functionality of Complex Assessment | General
NTE-0038 |  | EG-0012 | 2026-03-18T16:33:58.911Z | brooke.snow@commonspirit.org | Email sent to Corrinne Welch on 3/17/2026 to see if these changes are possible. | General
NTE-0039 | TSK-0036 |  | 2026-03-18T16:36:22.667Z | brooke.snow@commonspirit.org | Met with analyst 3/18 to review build and discuss questions. Email sent to Becky Leach to help complete build questions from analyst | General

## TaskActionItems
id | taskId | description | owner | dueDate | status | completedDate | notes | createdDate
TAI-0002 | TSK-0031 | Confirm the correct score for triggering an OPA on PHQA | Marty Koepke |  | Complete | 2026-03-12T15:49:43.454Z |  | 2026-03-11T22:25:05.899Z
TAI-0003 | TSK-0032 | Confirm with Kelly Bitonio the correct score for triggering interpretation on PHQA | Marty Koepke | 2026-03-13 | In Progress |  |  | 2026-03-11T22:36:52.791Z
TAI-0004 | TSK-0006 | Gold and OM meeting to review Design and ask questions | Brooke Searl | 2026-03-20 | In Progress |  | Brooke to set up meeting once all Gold analysts are identified | 2026-03-12T18:42:56.274Z
TAI-0005 | TSK-0012 | Meeting with analyst Megan Rutt to discuss missing EG ASAP documentation (pt neglect) | Jason Mihos | 2026-03-17 | Complete | 2026-03-17T19:21:34.670Z |  | 2026-03-13T20:38:09.618Z
TAI-0006 | TSK-0028 | How to configure Additional Cardiac Assessments | Brooke Searl |  | In Progress |  |  | 2026-03-17T17:22:55.896Z
TAI-0007 | TSK-0012 | In ASAP > Triage navigator > Behavioral Health element, for adult patients, add neglect questions (these questions are already available in Gold for ED pediatric patients) | Jason Mihos |  | Not Started |  |  | 2026-03-17T19:23:49.583Z

## TaskDocuments
id | taskId | documentName | documentType | url | dateAdded

## PRCC_Config
key | value
nextInitiativeId | 28
nextTaskId | 64
nextTaskNoteId | 40
nextTaskActionItemId | 8
nextTaskDocumentId | 1
nextTaskActionItemId | 1
nextTaskDocumentId | 1
nextInitiativeDocumentId | 17

## Master Missing Components Log
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Resolution Date | Notes
MCI-0001 | Nursing SOP Travel Screening | Need Foundation Travel Screening within Admission Navigator and Required Documentation | Clindoc | High | Alex Cordell | Brooke Snow | Analyst Assigned | No | Yes - Build can be complete | 2026-02-11 | Add in Foundation Travel screening to all admission navigators - FS Travel screening already aligns with Legacy Epic workflows
MCI-0002 | Candida auris | Candida auris screening OPA workflow | Primary - OPA Multiple Teams: Provider, Nurisng, Bugsy, reporting, Registration, HB | High |  | Brooke Snow | Identified | No | No - Did not meet with analyst |  |  |  | Working with OPA, Nursing, Infection Prevention/Bugsy, Reporting, Registration and HB analyst managers on resource identification This build went live in Legacy Epic 2/24/26 and is live in Cerner ECISA/CAREB in Janurary
MCI-0003 | Nurisng SOP Basic Neuro Assessment | Include LOC, Orientation Status, Facial symmetry, Speech, Cental nerves (corneal, cough, gag), DTR | Clindoc | High | Alex Cordell | Brooke Snow | Analyst Assigned | No | Yes - Build can be complete | 2026-02-11
MCI-0004 | Nurisng SOP Basic Cardiac Assessment | Update Cardiac Symptoms Update Chest Tubes LDA Include Implantable Cardiac Defibrillators | Clindoc | High |  | Brooke Snow | Identified | No | No - Did not meet with analyst
MCI-0005 | Nurisng SOP Fall Assessment | Fall interventions | Clindoc | High |  | Brooke Snow | Identified | No | No - Did not meet with analyst
MCI-0006 | Nursing SOP Skin | Intervention documentation mismatch | Clindoc | High |  | Brooke Snow | Identified | No | No - Did not meet with analyst
MCI-0007 | Suicide Policy | Social work/care coordination - CSSRS initial Screening OB - Are they using CSSR processes or DAST10? | Clindoc | High |  | Jason Mihos | Identified |  | No - Did not meet with analyst |  |  |  | For social work/care coordination, initial CSSRS access/documentation not needed -- this is done by nurses Regarding OB: DAST-10 is a drug-abuse screening tool, is not equivalent to Columbia suicide risk screen. System suicide risk policy applies to all acute areas and warrants use of CSSRS/Columbia tools, so this is what OB should be using
MCI-0008 | ED SOP | Abuse/neglect, violence screening -- neglect not included | ASAP, Clindoc | High |  | Jason Mihos | Identified |  | No - Did not meet with analyst
MCI-0009 | Bladder Management | Indications missing Epidural in Place, remove "Provider Managed" Nurse is able to place an IUC without a LIP Order. Not a clear place to document alternative management strategies attempted Order for Urinary Catheter does not have any required 'Criteria for Use' documentation requirements | Clindoc, Orders | High |  | Trudy Finch | Identified |  | No - Did not meet with analyst |  | Need orders analyst identified
MCI-0010 | SDOH | Social Drivers available in Storyboard for ED, Acute IP, Amb, Other HODs like OP Surgery, Infusion Centers. |  | High |  | Marty Koepke | Identified |  | Yes - Met with Analyst, Further build review needed | 3.10.26
MCI-0011 | SDOH | Social Drivers and Nursing Intervention questions available in Flowsheets for ED, Acute IP, Amb, Other HODs like OP Surgery, Infusion Centers. |  | High |  | Marty Koepke | Identified |  | Yes - Met with Analyst, Further build review needed | 3.10.26 | "Needs design review. Core CMS questions + observation of abuse question + nursing intervention questions available for RNs Only. Easiest conceived design is to have a single flowsheet that has all elements, with clear RN Only headers for Observation and nursing intervention sections. Needs some review. Appears that correct Social Drivers screening flowsheet has not been applied appropriately across positions/venues. EDRN in Gold TST do not have the correct flowsheet applied to preference list. "
MCI-0012 | SDOH | OPA work needed: - Acute/ED - Auto fire SW OPA when harm question answered + - Acute/ED - Auto fire SW OPA when patient answers + to wanting help for non safety questions. - Amb/HOD - Auto fire awareness OPA for providers when harm questions answered + - Amb/HOD - Auto fire awareness OPA to alert staff to place community referral |  | High |  | Marty Koepke | Identified |  | Yes - Met with Analyst, Further build review needed | 3.10.26 | Need best practice recommendation to alert providers that patient responded + to harm question, and/or are asking for support to non harm questions. Also to alert staff to create a community referral when patient is asking for support to non harm items.
MCI-0013 | SDOH | AVS - Add Find Help URL - All venues (ED, Acute, Amb, OP Depts where SDOH is screened) |  | High |  | Marty Koepke | Identified |  | Yes - Met with Analyst, Further build review needed | 3.10.26 | Need to determine if a print group for this exists for acute IP Gold.
MCI-0014 | Nursing SOP - Dialysis Graft/Fistula | Bruit/Thrill documentation for Graft/Fistulas | Clindoc | Medium | Corrinne Welch | Brooke Snow | Identified | No | No - Did not meet with analyst
MCI-0015 | Sedation Policy Narrator | Vital Signs - Missing ECO2 Waveform Pre-Procedure Checklist (ED) Rad Studies Available? Beta Blocker VTE Prophylaxis Normothermia Measures Stop Bang Sign In / Briefing - Missing Time Out Sign Out or Debriefing - Missing | Clindoc, ASAP, Rad, Lumens, Optime | Medium |  | Sherry Brennaman | Identified |  | No - Did not meet with analyst
MCI-0016 | Suicide Policy Dashboards | ED key metrics dashboard OB nurse manager dashboard Inpt quality nurse | Clindoc, Reporting | Medium |  | Jason Mihos | Identified |  | No - Did not meet with analyst |  |  |  | To my understanding, in February were still being built
MCI-0017 | Preferred Languages | Missing Languages: Persian Navajo Slightly Different Spelling: Punjabi (Spelled Panjabi) Urdu (Written as Urdu Pakistan) | Grand Central? | Medium |  | Marisa Radick | Identified |  | No - Did not meet with analyst
MCI-0018 | ICU Liberation | SAT Safety Screen SBT Safety Screen Early Progressive Mobility Protocol: Screen for Safety Daytime/Nightime Interventions - does this need to be documented in EHR? | Clindoc | Medium | Sara Garcia | Marisa Radick | Build In Progress |  | Yes - Build can be complete | 2026-02-11 | Sent two corrections back over to Sara on 2/26, awaiting her response to perform a final review
MCI-0019 | Valubles & Belongings | Policy Screenshots provided | Clindoc, ASAP, OpTime | Medium |  | Melissa Plummer | Identified
MCI-0020 | DAST10 | The DAST-10 tool is only found when searching the Database in Flowsheets Provider Notification also does not display and is only found in the Database when looking for Flowsheets Neither of the options when displayed in Flowsheets contains the Interventions as seen in FHS and CEN | Stork | Medium |  | Melissa Plummer | Identified

## Analyst Dashboard
Summary
Total Open Items | 18
Total Critical Items | 0
Total High Priority Items | 13
Items in Build in Progress | 1
Items Closed - Completed | 0
Items Closed - Deferred | 0
Breakdown by Analyst
Owner | Total Assigned | Open | Critical Open | Closed
Alex Cordell | 2 | 2 | 0 | 0
Amanda Davidson | 0 | 0 | 0 | 0
Christi Allen | 0 | 0 | 0 | 0
Christi Elsmore | 0 | 0 | 0 | 0
Corrinne Welch | 1 | 1 | 0 | 0
Gary Hudson | 0 | 0 | 0 | 0
Karan Patel | 0 | 0 | 0 | 0
Karen Sykes | 0 | 0 | 0 | 0
Kate Glass | 0 | 0 | 0 | 0
Maria Delacruz | 0 | 0 | 0 | 0
Mary Eckert | 0 | 0 | 0 | 0
Matthew Walsh | 0 | 0 | 0 | 0
Myra Ventrcek | 0 | 0 | 0 | 0
Pam Shadle | 0 | 0 | 0 | 0
Patrick McGovern | 0 | 0 | 0 | 0
Racquel Calhoun | 0 | 0 | 0 | 0
Ryan Carr | 0 | 0 | 0 | 0
Sara Garcia | 1 | 1 | 0 | 0
Sheron Johnson | 0 | 0 | 0 | 0

## Amanda Davidson
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Other Modules/Analyst | Downstream Impacts | Affected Epic ID's | Build Questions

## Alex Cordell
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Other Modules/Analyst | Downstream Impacts | Affected Epic ID's | Build Questions
MCI-0001 | Nursing SOP Travel Screening | Need Foundation Travel Screening within Admission Navigator and Required Documentation | Clindoc | High | Alex Cordell | Brooke Snow | Analyst Assigned | No | Yes - Build can be complete | 02/11/2026 | Add in Foundation Travel screening to all admission navigators - FS Travel screening already aligns with Legacy Epic workflows | Gold Build: EHR Content Review- Core Nursing SOP | Beaker - John Snow Bugsy - Shawn Johnson
MCI-0003 | Nurisng SOP Basic Neuro Assessment | Include LOC, Orientation Status, Facial symmetry, Speech, Cental nerves (corneal, cough, gag), DTR | Clindoc | High | Alex Cordell | Brooke Snow | Analyst Assigned | No | Yes - Build can be complete | 02/11/2026 |  | Gold Build: EHR Content Review- Core Nursing SOP

## Christi Allen
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Christi Elsmore
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Corrine Welch
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions
MCI-0014 | Nursing SOP - Dialysis Graft/Fistula | Bruit/Thrill documentation for Graft/Fistulas | Clindoc | Medium | Corrinne Welch | Brooke Snow | Identified | No | No - Did not meet with analyst

## Gary Hudson
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Karan Patel
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Karen Sykes
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Kate Glass
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Maria Delacruz
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Mary Eckert
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Matthew Walsh
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Myra Ventrcek
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Pam Shadle
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Patrick McGovern
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Racquel Calhoun
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Ryan Carr
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Sara Garcia
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions
MCI-0018 | ICU Liberation | SAT Safety Screen SBT Safety Screen Early Progressive Mobility Protocol: Screen for Safety Daytime/Nightime Interventions - does this need to be documented in EHR? | Clindoc | Medium | Sara Garcia | Marisa Radick | Build In Progress |  | Yes - Build can be complete | 2/11/26 | Sent two corrections back over to Sara on 2/26, awaiting her response to perform a final review

## Sheron Johnson
ID | CSH Policy | Detailed Description/Missing Fields | Module | Priority | Primary Analyst | Primary SCI | Status | End User Education Required? | Analyst/SCI Initial Build Review Complete | Analyst/SCI Build Review Meeting Date | Action Items for Resolution | Crosswalk | Downstream Impacts | Affected Epic ID's | Build Questions

## Archived Components
ID | Missing Component | Detailed Description | Module | Priority | Primary Analyst | Primary SCI | Status | Downstream Impacts | Affected Epic ID's | Build Questions | Resolution Date | Action Items for Resolution | Notes
| Oral Kleen | Missing Oral Mucisal care and Tongue Scraping | Clindoc | Medium |  | Sherry Brennaman | Closed - Completed | [5 empty] | Crosswalk
| Age Friendly | Turbocharger package needed;expanded SDOH questions with age based criteria; | Multiple Apps | High |  | Dawn Jacobson | Closed - Deferred

## CSH PSG
IT Indicated in Gold | System Policy/Standard/Guideline | Type | Priority | Confirmed in Gold (Validated) | SCI Point of Contact | Analyst | Application | Specialty/Primary Impacted Dept./Discipline | Specialized Workflow Needed? | Brief Details | Link to Policy/ Guideline | Intake Slide | Link to Document/ EHR Requirements | System Sponsor | Comments/Follow-up | CSH Standards of Practice - https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice
| E-Signature in Epic Templates |  | 1 |  | Ashley Hubbard |  | Orders | Provider/Nursing
| Antimicrobial Steardship for ARTIs |  | 1 |  | Ashley Hubbard |  | Willow / Orders | Pharmacy | No
| C-Auris | Guideline | 1 | No | Brooke Snow |  | Clin Doc / Orders | Provider/Nursing | Yes |  |  | System Initiative Candida auris | Candida auris _SCI Workbook | Becky Leach | Each Epic instance has slightly different build - need to finalize build and workflow with Bugsy piece included in order to finalize Gold build
| Core Nursing - Standard of Practice |  | 1 | Yes | Brooke Snow & Marisa Radick |  | Clin Doc | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice CommonSpirit Core Nursing Standards of Practice.docx |  | Gold Build: EHR Content Review- Core Nursing SOP
| Yale Swallow Screen | Policy | 1 | Yes | Dawn Jacobson |  | Clin Doc | Provider/Nursing | No | Via email on 11/20. Christi confirmed in Gold, and will remove TF as exclusion criteria. 2.11 - Stroke Narrator does not contain Yale Swallow Screening. ASAP team is replacing the current screening documentation with Yale for Wave 3.
| Age Friendly Documentation | Board Goal | 1 | No | Dawn Jacobson |  | Clindoc | Provider/Nursing | Yes
Yes | Suicide Risk Policy | Policy | 1 | Yes | Jason & Sherry |  | Clin Doc | BHU/Nursing | Yes | See details. Note: No decisions yet as to which dashboards in Epic Gold will update with which suicide risk details | Clinical A-025 Identifying and Assessing Patients at Risk of Suicide-Self-Harm PandP PENDING |  |  | Paul Rains
| Emergency Services - Standard of Practice | Standards of practice | 1 | Yes | Jason Mihos & Sherry Brennaman |  | ASAP | ED nursing | No | See details. Questions about next steps (ED SoP updates needed?) -- will confirm with Tiffany | CSH Emergency Department Nursing Standards of Practice -FInal.docx
| Bladder Management | Policy | 1 | No | Trudy Finch |  | Clin Doc / Orders | Provider/Nursing | Yes | Ensuring the Indications from policy are in Gold | Bladder Management Policy.pdf https://commonspirit-national.policystat.com/policy/13986669/latest#autoid-rdymk |  | EHR Content | Rebecca Leach | Nursing-Missing 'Reason for Continuing IUC" = Epidural in Place. Policy does not recognize "Provider Managed" as a reason to continue. Nurse is able to place an IUC without a LIP Order. Not a clear place to document alternative management strategies attempted. Provider-The order for Urinary Catheter does not have any required 'Criteria for Use' documentation requirements.
| Perioperative - Standard of Practice |  | 1 |  | Kim Wilis |  |  | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice 4. Perioperative Nursing Standards of Practice (Preop, Intraop, Postop) Final
| ICU Liberation | Guideline | 1 | Yes | Marisa Radick |  | Clin Doc / Orders | Critical Care | Yes | Ensuring elements of the A-F bundle are built in Gold | CSH ICU Liberation ABCDEF Bundle Clinical Guidelines -Update Draft 2024).docx | Intake Slide ALM 4139 |  | Brenda Downs | See tab for missing elements of bundle Met with clin doc analysts on 2/11 to review needed build changes
| Valuables and Belongings | Policy | 1 | No | Melissa Plummer |  | Clin Doc | Nursing | Yes | Discharge for ED and for IP missing itemized list of pt belongings. Standardized Essential belongings not in Periop. - SEE Valuables & Belongings Tab | Template On Hold for V&B
| DAST-10 tool |  | 1 | No | Melissa Plummer |  | Clin Doc | BHU/Nursing/Stork | Yes | Not in Epic Gold SEE Dast-10 Tab | No National Policy or Guideline
| Perinatal - Standad of Practice |  | 1 | No | Melissa Plummer & Robin DeLorenzo |  |  | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice |  |  |  | Attached link does direct to site for SOP, however when clicking on Perinatal, the user is directed to WICI Institute page, which does not include SOP. VMMC does not have OB dept. Primary care may offer OB/GYN services, but patients are sent to FHS or another facility for delivery.
| Telemetry | Policy | 1 |  | Nicole Johnson |  | Clin Doc / Orders | Provider/Nursing | Yes
Yes | Vascular Access | Policy | 1 | Yes | Robin DeLorenzo |  | Clin Doc / Orders | Provider/Nursing | No |  | Clinical A-012 Vascular Access Selection, Adult POLICY w-Att 072722.pdf |  |  |  | There is a DMND that is in progress to match the policy
| Extravasavation Tx | Policy | 1 | Yes | Robin DeLorenzo |  | Clin Doc / Orders | Provider/Nursing | Yes | [5 empty] | A DMND is in progress to update the interventions per policy
| AMPAC Tool | Documentation | 1 | Yes | Robin DeLorenzo |  | Therapies OT,PT, SLP | Therapy | No | a documentation tool in Flowsheets needs licensure not approved |  |  |  |  | This is present in GOLD TST under therapy login
| Pediatric - Standards of Practice |  | 1 | No | Robin DeLorenzo & Melissa Plummer |  |  | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice |  |  |  | VMMC does not currently have a PEDs dept. There are clinics but the SOP is specific to IP.
| Details Will require multiple modules (ASAP, Interventional Radiology, Lumens, all Procedural areas). 5-10 hours of updates for each impacted team. Will require update to procedral narrators and Sedation Narrator | Policy | 1 | No | Sherry Brennaman |  | Clin Doc | Provider/Nursing | Yes | Details Will require multiple modules (ASAP, Interventional Radiology, Lumens, all Procedural areas) | Moderate and Deep Sedation SCI Workbook
| Point Click Care (State of Washington-EDIE (ED Information Exchange for WA State) | Epic Best Practice | 1 | Yes | Sherry Brennaman |  | Clin Doc / Orders / Willow | Provider/Nursing/Pharmacy | Yes | Care Coordination is requesting to be included in this work
| HAPI | Policy | 1 | Yes | Trudy Finch |  | Clin Doc / Orders | Provider/Nursing | Yes |  | Facility Template Policy - Hospital Acquired Pressure Injury (HAPI) Management EDITED.pdf |  | https://drive.google.com/drive/folders/1JlJahX8YcyVko8eoEKoS0iyyDbiPq_g3?usp=drive_link
| Chemo Policy | Policy | 1 | Yes | Trudy Finch |  | Oncology | Oncology | No | Work with Yvette | Antineoplastic -Chemotherapy - Immunotherapy- Prescribing and Administration for Oncology Indications POLICY- Clinical A-027.pdf | Antineoplastic -Chemotherapy - Immunotherapy- Prescribing and Administration for Oncology Indications PROCEDURE- Clinical A-027P.pdf
Yes | Vesicants | Policy | 1 | Yes | Van Nguyen |  | Clin Doc / Orders / Willow | Provider/Nursing/Pharmacy | Yes with Extravasation | vesicant meds identifed on the MAR | Alpha--Vesicant List Extravasation - Management and Treatment Guidance.docx
| Oncology Flowsheet | CAT Decisions | 1 | Yes | Yvette Kirk |  | Oncology |  | Yes | Chemo Admin |  |  |  | Lise/Marcia | Submitted viaTask Force
| CMU Virtual Telemetry - GE Carescape/Ascom | Project | 2 |  | Brooke Snow |  | Clin Doc / Orders | Provider/Nursing | Yes | Virtual Telemetry units monitored from CareBase in AZ | Project number: 1014176_0011081 |  |  | Gail Daily
| Virtually Integrated Care | Best Practice | 2 |  | Brooke Snow |  | Clin Doc / Orders | Provider/Nursing | Yes | Security Set up to identify virtual nurses
| SDOH | Guidelines | 2 | No | Marty Koepke |  | Clin Doc | Patient Care Services | Yes | Missing OPA for SW when safety responses are positive. |  |  |  |  | "For Non Harm questions > when Pt responds YES that they want a community, we need an OPA > Referral to SW. Community resource link needs to be available in Social Drivers to support WFs adding community resources to After Visit Summary. When SDOH driver responses score high enough across any/all domains an OPA fires for referral to SW. Should we adopt this for Gold? Previous Decision made? "
| Sepsis Protocol | Guideline | 2 |  | Marisa Radick |  | Clin Doc / Orders | Provider/Nursing | Yes |  | https://commonspirit-national.policystat.com/policy/18612396/latest#autoid-z4rar |  |  | Brenda Downs
| Preferred Language | Policy | 2 | Yes | Marisa Radick |  | Nursing | Patient Care Services | No | Ensuring the threshold languages are built in Gold |  |  |  | Lisa Macri | See tab for missing languages
| Critical Care - Standard of Practice |  | 2 |  | Marisa Radick & Brooke Snow |  |  | Nursing | No |  | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice CommonSpirit Critical Care Nursing Standards of Practice Final-Approved Header.docx
| RT Pulmonary Mechanics | Requested by System Leader | 2 |  | Marty Koepke |  | Clin Doc | RT | Yes? | Work with Gold Analysts and System leaders for details
| Drug Screen Order for OB | Ticket # | 2 |  | Melissa |  | Stork | OB | Yes |  |  |  |  | Mindy Foster | Submitted viaTask Force
| Admit to NICU- precheck Vitamin K | Ticket # | 2 |  | Melissa |  | Stork | NICU | No | From SCOPE - Talk Diedre about details |  | Mountain Admit to Neonatal ICU order set updates
| National Numbers on AVS | Requested by System Individual | 2 |  | Melissa Plummer |  | Clin Doc | Nursing | No | List of standard national numbers needed on AVS | National Hotline Numbers- Epic Gold |  |  | Holly Gibbs/ Connie | Submitted viaTask Force-Check what is built, f/u with Tiff
| Outpatient in a bed | Requested by System VP Care Coordination | 2 |  | Melissa Plummer |  | Clin Doc | Care Coordination/Provider | Yes | Single order for outpatient in a bed | Copy of OIB Guidance - Final.docx |  |  | Gail Moxley | Submitted viaTask Force-does it match current updates to guideline?
| OralKleen (Comprehensive Oral Care) | Policy | 2 | No | Sherry Brennaman |  | Clin Doc | Nursing | No | Missing 2 options in Oral Care respose. Being updated for Wave 3. | Comprehensive Oral Care SCI Workbook
| Antimicrobial Prophylaxis Guidelines | Guidelines | 2 | No | Van |  | Willow / Orders | Pharmacy | No
| REMS Medications and Denials |  | 2 | No | Van |  | Willow | Pharmacy | No | this was not approved to be built in any envionrment yet. not in MTN in current state so not slated for GOLD. DMND0007976 is assigned 4- low priority at this time
| Quality Reporting |  | 2 |  | Team |  |  | Quality | No | Top 25 Quality Reports | Quality Priority Reporting Build Review-Epic Gold New Instance |  |  | Tracy Sklarr | Due on February 6, 2026
| Epic Denial Work Queue | Ticket # | 3 |  | Marisa Radick |  | Grand Central/ Prelude? | Rev Cycle |  |  |  | Epic Denial Work Queue Intake Slides |  | Diane Pirak
| HAPI RT Devices | System Request | N/A |  | Marty Koepke |  | Clin Doc | RT | No | Awaiting Final Design for Epic | [6 empty] | Epic Gold -> | Drive
| Harm to Others Policy | Policy | N/A |  |  |  | Clin Doc | BHU/Nursing | Yes | Awaiting Final Design - Let's make sure |  |  |  | Paul Rains | Design Not Complete

## References
Testing | Resources | Test Scripts (If Applicable)
CSH Policy/Published Guidelines | https://commonspirit-national.policystat.com/
CSH Standards of Practice | https://sites.google.com/commonspirit.org/nnpatientcareservices/home/professional-practice/standards-of-practice
Core Nursing SOP | CommonSpirit Core Nursing Standards of Practice.docx
O&M Promised for Gold
High Risk and Problematic Workflows such as: Medication Reconciliation, Blood Transfusion, DM Management etc.
Most Common Workflows such as: Admissions, Transfers, Discharges
Meet with Epic Gold Analysts that did the build | Clin Doc Team

## Dashboard
EPIC GOLD INITIATIVES DASHBOARD
Updated: Mar 18, 2026
Total Initiatives | Total Tasks | Tasks w/ Analyst | Tasks Unassigned | High Priority Init. | Init. Completed
23 | 52 | 18 | 34 | 14 | 0
INITIATIVE STATUS | Count | % |  | TASK STATUS | Count | % | INITIATIVE TYPE | Count | %
In Progress | 0 | 0% |  | Identified | 43 | 82.69% | Standard Practice | 11 | 47.83%
Under Review | 0 | 0% |  | Analyst Assigned | 2 | 3.846% | Policy | 6 | 26.09%
Ready for Discussion | 0 | 0% |  | Build In Progress | 2 | 3.846% | Guideline | 5 | 21.74%
Not Started | 0 | 0% |  | Build Analyst Assigned | 3 | 5.769% | Board Goal | 1 | 4.348%
Completed | 0 | 0% |  | Closed - Completed | 1 | 1.923%
|  |  |  | Dismissed | 1 | 1.923%
INITIATIVE PRIORITY | Count | % |  | GO-LIVE WAVE | Count | % | BUILD REVIEW STATUS | Count | %
High | 14 | 60.87% |  | Wave 3 | 0 | 0% | In Progress | 16 | 30.77%
Medium | 9 | 39.13% |  | New Beginnings South | 0 | 0% | Yes - Build can be complete | 5 | 9.615%
Low | 0 | 0% |  |  |  |  | No - Did not meet | 20 | 38.46%
[7 empty] | (blank) | 951 | 1829%
ANALYST WORKLOAD (Tasks) | Tasks | % of Total |  | MODULE BREAKDOWN (Tasks) | Tasks | % of Total | EDUCATION REQUIRED | Count | % of Total
Alex Cordell | 6 | 11.54% |  | ClinDoc | 21 | 40.38% | Yes | 12 | 23.08%
Michelle Ryan | 2 | 3.846% |  | OPA | 7 | 13.46% | No | 29 | 55.77%
Christi Allen | 2 | 3.846% |  | ASAP | 4 | 7.692%
Megan Rutt | 1 | 1.923% |  | Stork | 3 | 5.769%
Corrinne Welch | 1 | 1.923% |  | Orders | 3 | 5.769%
Sara Garcia | 1 | 1.923% |  | Grand Central | 1 | 1.923%
Adam Henderson | 2 | 3.846% |  | Bugsy | 1 | 1.923%
Jennifer Brennan | 1 | 1.923% |  | (blank/TBD) | 952 | 1831%
Jared Boynton | 1 | 1.923%
Desiree Upton | 1 | 1.923%
(Unassigned) | 34 | 65.38%
VENUE ANALYSIS (Initiatives) | Count | % |  | SCI LEAD WORKLOAD (Init.) | Count | %
Acute Inpatient Only | 8 | 34.78% |  | Brooke Searl | 8 | 34.78%
ED Only | 1 | 4.348% |  | Marty Koepke | 5 | 21.74%
Ambulatory Only | 3 | 13.04% |  | Jason Mihos | 2 | 8.696%
Periop Only | 1 | 4.348% |  | Marisa Radick | 2 | 8.696%
Cross-Venue (multiple) | 6 | 26.09% |  | Melissa Plummer | 2 | 8.696%
(blank) | 977 | 4248% |  | Sherry Brennaman | 2 | 8.696%
|  |  |  | Trudy Finch | 1 | 4.348%
|  |  |  | Dawn Jacobson | 1 | 4.348%