## Initiatives
id | name | description | initiativeType | stage | priority | status | governanceTicket | almLink | dateReceived | targetDate | assignedTo | secondaryAssigned | driveFolderLink | ehr | serviceLine | effortSize | createdAt | updatedAt
INI-0001 | HAPI RT O2 Skin Assessments | streamline Epic RT skin assessment documentation to be minimal | System Initiative | Build | High | On Track | FETR0111279 | https://docs.google.com/spreadsheets/d/1ViIedhzeNyOrOKTpMj_TXzQNT97N2WoDktMmPhgLcH4/edit?gid=0#gid=0 |  | 2026-05-15 | Marty Koepke |  | https://drive.google.com/drive/folders/1GlOOeTrkpQug1nMDzyUJp6mzEVvzHYKd | Epic | Ancillary | S - 1-2 hrs/wk | 2026-02-09T21:59:32.902Z | 2026-02-12T01:47:35.656Z
INI-0002 | Amb Epic Gold WF Review | Evaluating Epic Gold for Ambulatory against system standards | Epic Gold | Validation | Critical | On Track | NA |  |  |  | Marty Koepke |  | https://drive.google.com/drive/folders/1PbRBbyNGS1EIwPtUvebG2inL3tN4JlRj | Epic | Ambulatory | L - 6-10 hrs/wk |  | 2026-02-12T02:29:40.838Z | 2026-02-09T23:15:41.589Z | 2026-02-09T23:15:41.589Z
INI-0003 | PUP Health Maintenance Group | Cerner Health Maintenance Ownership Group | Consultation | Governance | Low | On Track |  |  |  |  | Marty Koepke |  |  | Cerner | Ambulatory |  |  | 2026-02-12T01:49:32.775Z | 2026-02-10T00:18:46.415Z | 2026-02-10T00:18:46.415Z
INI-0004 | Abuse, Neglect and Violence | Clean up redundant EHR content to better align with SDOH standard | System Initiative | Intake | Medium | On Track |  | Clean up redundant EHR content to better align with SDOH standard |  |  | Marty Koepke | Melissa Plummer |  | All | Acute Institute | S - 1-2 hrs/wk |  | 2026-02-12T01:50:25.295Z | 2026-02-10T00:23:18.071Z | 2026-02-10T00:23:18.071Z
INI-0005 | Interpreter Services Optimization | Achieve CSH defined standard for documenting translation services in Epic Gold | Epic Gold | Business Case | High | On Track |  | https://docs.google.com/spreadsheets/d/1fbwBgPteaPWnmdkzz1-2J4JA0878oRDj3cv_7-5XKrE/edit?userstoinvite=connie.clemmonsbrown%40commonspirit.org&role=writer&gid=0#gid=0 |  | 2026-05-01 | Marty Koepke | Melissa Plummer | https://drive.google.com/drive/folders/11poDwVlKnclZtuDdkQgPRLxxs8TMyZ4d | Epic | Acute Institute | S - 1-2 hrs/wk |  | 2026-02-12T01:51:29.152Z | 2026-02-10T00:24:15.534Z | 2026-02-10T00:24:15.534Z
INI-0006 | SDOH CSH Standards | Implement CSH Standards for SDOH across all platforms and venues | System Initiative | EHR Requirements | Medium | At Risk | DMND0005853 | https://docs.google.com/document/d/1NLW64iNDCQssY-0IKGu7vx99jFzuRLDP16wl0Y3Ab6k/edit?tab=t.0 |  |  | Marty Koepke | Melissa Plummer | https://drive.google.com/drive/folders/1QPBjW6lAO3z6CL8eqFVeveLHcdyfFKPq | All | Other | L - 6-10 hrs/wk |  | 2026-02-17T19:08:01.664Z | 2026-02-10T00:25:26.265Z | 2026-02-10T00:25:26.265Z
INI-0007 | Natera Project (CAREB Only) | Bi-Directional orders interface between Natera and Cerner | Consultation | Validation | Medium | On Track |  | https://docs.google.com/document/d/1VlanCu1Pw7poCZDhSiB6lTo9fGZARl4qQ2WTCAU6kJs/edit?tab=t.0#heading=h.s0uffrch7dlu |  |  | Marty Koepke |  |  | Cerner | Ambulatory | XS - Less than 1 hr/wk |  | 2026-02-12T02:23:00.838Z | 2026-02-10T00:26:13.252Z | 2026-02-10T00:26:13.252Z
INI-0008 | Abridge Ambient AI | Ambient AI software to support improved provider documentation | System Project | Adoption | Medium | On Track |  | https://drive.google.com/drive/folders/15vOauNUfs0P8RVd_KlkdMA3DzG5SR_mr |  |  | Marty Koepke |  |  | All | Other | S - 1-2 hrs/wk | https://drive.google.com/drive/folders/1bL1W29TQxvwm28mMWC1EdzkXb8eNeY_0 | 2026-02-19T21:08:45.289Z | 2026-02-10T01:07:35.146Z | 2026-02-10T01:07:35.146Z
INI-0009 | HRS EPIC Integration Project PRJ0012291 | Integrate HRS enrollment and return notes to Epic Gold | Epic Gold | Build | Critical | At Risk | PRJ0012291 | https://docs.google.com/presentation/d/1uwctki9VnCScwgHTCsbs2JufbWySSLjEj9J7aNvXg-w/edit?slide=id.geaa92738cc_0_0#slide=id.geaa92738cc_0_0 |  | 2026-05-01 | Marty Koepke |  | https://drive.google.com/drive/folders/1pUzbvg1LmJhAO_j89a21LCHAWkAkmkxH | Epic | Ambulatory | M - 2-5 hrs/wk |  | 2026-02-12T02:23:56.933Z | 2026-02-10T18:11:05.458Z | 2026-02-10T18:11:05.458Z
INI-0010 | Depression Interpretation Optimizations | Need to determine what is happening in Epic Gold for Depression screening interpretations | Consultation | Business Case | Medium | On Track |  | https://docs.google.com/presentation/d/1H2ne-6bEGeWlxK4eU3yXUhRVKle03B1MlNOjJlFrGhQ/edit?slide=id.g2ccdbaf18e2_0_322#slide=id.g2ccdbaf18e2_0_322 |  |  | Marty Koepke |  |  | All | Ambulatory | S - 1-2 hrs/wk |  | 2026-02-12T02:24:39.326Z | 2026-02-10T18:23:54.287Z | 2026-02-10T18:23:54.287Z
INI-0011 | IRF Education Documentation Review and Management (ALM 1970) | Researching Status and Goals | Consultation | Design | Medium | Dismissed | DMND0007442 | https://docs.google.com/presentation/u/0/d/1T1RN0hUWRB_d1A8ZhSf03k1pnkvdQwVqgVPG-vjksok/edit |  |  | Marty Koepke |  |  | Cerner | Ancillary | XS - Less than 1 hr/wk | https://drive.google.com/drive/folders/13ot_u3qss92iJBcB92EG-FTZ3eeSVgA6?usp=drive_link | 2026-02-18T23:18:33.669Z | 2026-02-10T18:59:04.043Z | 2026-02-10T18:59:04.043Z
INI-0012 | CMU Tele-Strips Optimization Cerner | Following the implementation of CMU Rhythm strip integration into Cerner, complaints from inpatient physicians that interfaced rhythm strips are flooding the Cardiology section of Results Review and the Diagnostics WF component, making it difficult to find actual EKGs and Echos. | Market Initiative | Prioritization | Low | On Track | DMND0008941 | https://docs.google.com/presentation/d/1MILT100wTz1CZX4Gp9L7iyz8mTzeVdTBq5H3DLtSjhI/edit?slide=id.g2ccdbaf18e2_0_322#slide=id.g2ccdbaf18e2_0_322 |  |  | Marty Koepke |  | https://drive.google.com/drive/folders/1TsewWXbZQbpi810rk2uolEGQtDCxbeHc | Cerner | Acute Institute | XS - Less than 1 hr/wk |  | 2026-02-12T02:25:53.727Z | 2026-02-11T18:07:39.333Z | 2026-02-11T18:07:39.333Z
INI-0013 | HRS Cerner Integration | Post Go Live Expansion Consult Activities | Consultation | Adoption | Medium | On Track | NA | RITM7164302- CPOE Request |  |  | Marty Koepke |  |  | Cerner | Ambulatory | XS - Less than 1 hr/wk |  | 2026-02-12T02:26:46.134Z | 2026-02-11T18:31:29.905Z | 2026-02-11T18:31:29.905Z
INI-0014 | Abridge AI - Org Expansion | Initial pilot considered successful. Completed. This work is related to ongoing expansion to ED, maybe RNs, and additional clinics. | System Initiative | Team Assignment | Medium | On Track | NA |  |  |  | Marty Koepke | Jason Mihos | https://drive.google.com/drive/folders/1bL1W29TQxvwm28mMWC1EdzkXb8eNeY_0 | All | Other | M - 2-5 hrs/wk |  | 2026-02-12T02:27:40.739Z | 2026-02-11T19:32:52.483Z | 2026-02-11T19:32:52.483Z
INI-0015 | Vaccine Deferral (All Platforms) | Evaluate how the EHR handles vaccine/Immz deferrals/declines. | SCI Team | Team Assignment | Critical | On Track |  |  | 2026-02-12 | 2026-02-18 | [8 empty] | 2026-02-12T17:57:13.382Z | 2026-02-12T17:57:13.382Z
INI-0016 | Zoom Integration Update Needs | We were referred to you regarding planned enhancements for the Cerner Zoom integration at Dignity Health. We understand you were involved in code changes for this workflow that were tested successfully but never moved to production around 3-4 years back. Background: We are currently working to decommission Axway APIM by March and migrate all APIs to Mulesoft. The Cerner Telehealth integration is one of the final pieces remaining on Axway. While the Mulesoft development is complete, we have identified necessary changes on the consumer side (backend .NET code). In consulting with Gregg and Orlando, we discovered that several enhancements made 3-4 years ago were never deployed to production. Unfortunately, it is not possible to revert these components due to inadequate source code management tools used at that time, to focus solely on the Axway-to-Mulesoft migration. Consequently, we cannot move away from Axway without also deploying these legacy enhancements. Given the limited timeframe, we need to find a way to test these changes and workflows to ensure there is no impact on the telehealth service. Your insights on how to proceed with testing would be greatly appreciated. Let me know if a meeting is needed to align on this. | Consultation | Intake | Critical | On Track |  |  | 2026-02-17 | [6 empty] | Cerner | Ambulatory | M - 2-5 hrs/wk | 2026-02-17T22:03:52.980Z | 2026-02-17T22:03:52.980Z
INI-0017 | Testing The Initiative Dashboard | This is a description of the work that needs to be done | Consultation | Business Case | Medium | On Track | GOV-1234 |  | 2026-02-19 |  | Jane Smith |  |  |  |  | All | Other | S - 1-2 hrs/wk | 2026-02-19T23:24:22.536Z | 2026-02-19T23:24:22.536Z

## ActionItems
id | initiativeId | task | owner | dueDate | status | completedDate | calendarEventId | notes | createdAt
ACT-0002 | INI-0001 | CI communication to Orgs | Group | 2026-02-27 | Complete | 2026-02-13T18:00:38.177Z | a2nrvb236eirhivsmkv5fph1vk@google.com | Ensure CIs have enough information to round with local stakeholders | 2026-02-09T22:40:09.694Z
ACT-0006 | INI-0005 | FU with Lisa Macri | Marty Koepke | 2026-02-13 | Complete | 2026-02-11T17:18:07.675Z | 6hq3vmq4hlreaegj5kqajmp32c@google.com | Status update between Lisa and Connie | 2026-02-10T00:28:02.026Z
ACT-0007 | INI-0003 | Notable Feasibility Check: 18-21 year old adult wellness visits, | Marty Koepke | 2026-02-10 | Complete | 2026-02-10T20:03:18.388Z | ukdsvaak33imghnrbo07na76fk@google.com | Investigate and propose the best approach (registry, notable push, RPA, or combined) for tracking and prompting 18-21 year old adult wellness visits, including assessment of governance requirements and potential for bundling with other health maintenance optimization requests. | 2026-02-10T00:45:32.623Z
ACT-0008 | INI-0001 | just testing | Marty Koepke | 2026-02-10 | Complete | 2026-02-10T01:04:31.921Z | fvf07k7sru09ks1cr1nnfnpsl8@google.com | seeing what can be done | marty,koepke@commonspirit.org | 2026-02-10T01:03:44.248Z
ACT-0010 | INI-0007 | Natera FU: Email Seshat and Mike D. | Marty Koepke | 2026-03-20 | Not Started |  | ebiipfk75beji6mdie4lol106c@google.com | Get update on overall progress. We are currently finalizing testing and working to complete the following by March 23rd: - Updated OBR7 segment issues - Message pool testing - Order defaulting and activation Additionally, testing, change control, and PICA must be completed. | marty.koepke@commonspirit.org | 2026-02-10T18:20:40.613Z
ACT-0011 | INI-0010 | Review Depression Screening Interpretation WF in EG | Marty Koepke | 2026-02-10 | Complete | 2026-02-10T23:24:43.781Z | 94oti7kaa19mpj8tmtpfo3npug@google.com |  | marty.koepke@commonspirit.org | 2026-02-10T18:26:57.403Z
ACT-0012 | INI-0011 | IRF Education Doc in Cerner (Review with Tiff) | Marty Koepke | 2026-02-11 | Complete | 2026-02-12T18:34:53.619Z | g4m6hmb7nph6f72ar4b8u4g4qs@google.com | what do we do now? | marty.koepke@commonspirit.org | 2026-02-10T21:25:09.286Z
ACT-0016 | INI-0010 | Evaluate Current open Epic Ticket to Determine if should be system embedded | Marty Koepke | 2026-02-13 | Complete | 2026-02-12T16:41:33.496Z | qeej2rah9nmblqfnlgqj6j4nk4@google.com |  | marty.koepke@commonspirit.org | 2026-02-11T20:19:29.295Z
ACT-0018 | INI-0009 | HRS SBAR: Confirm Status of SBAR request | PJ Harrison | 2026-02-20 | Complete | 2026-02-18T17:03:36.912Z | v51mthobkt1csv7i21h9u56ea0@google.com | Remember to check in with Epic Gold SBAR review committee for status on HRS scope change | marty.koepke@commonspirit.org | Follow-Up | 2026-02-11T22:11:04.291Z
ACT-0019 | INI-0010 | Meet with Nicole Johnson assigned to open Epic ticket for Depression Screening and FU. | Marty Koepke | 2026-02-13 | Complete | 2026-02-12T23:32:17.841Z | lkr8b77tvaol0i1c7lt8abqqec@google.com | Review business case and desired outcomes of open request. Determine if request for Cerner could be bundled into Epic request. | marty.koepke@commonspirit.org | Action Item | 2026-02-12T16:41:22.809Z
ACT-0020 | INI-0002 | Find CSH Clinical Standards Documentation (BP, Depression, TCM, MAWV) | Marty Koepke | 2026-02-20 | Complete | 2026-02-12T19:59:34.936Z | 32fetut40qp46d7g3dd1jv408k@google.com |  |  | Follow-Up | 2026-02-12T18:20:15.353Z
ACT-0021 | INI-0002 | ID Source of Truth for EG Workflows [Partner with Instructional Designers] | Cyndi Melden | 2026-02-20 | Complete | 2026-02-18T17:06:25.713Z | 4n76pb863fl0t7i0ena3l7m5c4@google.com | Reach out to instructional design team for Epic Gold. Determine their source of truth for EG Amb WFs. | marty.koepke@commonspirit.org | Action Item | 2026-02-12T18:22:35.646Z
ACT-0022 | INI-0002 | EG Amb WF: Review Quality Drive Folders | Jessica Merritt | 2026-02-17 | Complete | 2026-02-17T19:19:11.763Z | rtom0s7oqtkbbdo8qc42dulunc@google.com | Try and find solid CSH clinical and EHR standards for Depression and BP | jessica.merritt2@commonspirit.org,, marty.koepke@commonspirit.org | Action Item | 2026-02-12T20:02:07.973Z
ACT-0023 | INI-0002 | EG Amb WF: Continue Depression Interp Behvior | Norah Loker | 2026-02-17 | Complete | 2026-02-18T17:12:41.324Z | v364gr01ciaikefu3j50qdakk8@google.com | Continue testing depression OPAs for Adult and Peds. Document outcomes and be ready to report out next week | norah.loker@commonspirit.org, marty.koepke@commonspirit.org | Action Item | 2026-02-12T20:03:56.410Z
ACT-0024 | INI-0002 | EG Amb WF: Begin testing on clinic administered meds | Ashley Crouse | 2026-02-17 | Complete | 2026-02-18T17:12:43.286Z | oc0l1gs4atf2j616e5eka9dda8@google.com | Test EG against identified policy. Document findings and be ready to report out. https://docs.google.com/spreadsheets/d/1lQqOmB_wUOP5BU90Zf7AUJmD3CBBGQcW9YEyAalpakg/edit?gid=1473215283#gid=1473215283 | ashley.crouse@commonspirit.org, marty.koepke@commonspirit.org | Action Item | 2026-02-12T20:05:59.103Z
ACT-0025 | INI-0001 | Schedule working sessions with Group and Karen Sykes. | Marty Koepke | 2026-02-17 | Complete | 2026-02-17T19:44:02.785Z | tdc5t0cjeg4968ksk0fmc4jnrg@google.com | Proposed concept will not completely work. Wound documentation concept is sound. Need a way to connect specific device type with skin integrity issues. also need to consider ideal flowsheet and groups on each flowsheet for streamlined documentation experience. | marty.koepke@commonspirit.org | Action Item | 2026-02-13T18:03:26.207Z
ACT-0026 | INI-0004 | Reach out to Risk Regarding Mandated Reporting Documentation | Marty Koepke | 2026-02-27 | Complete |  | n4f7pe2m8n7l5u7s1iag633bg8@google.com | Holly is willing to, but we need more information | marty.koepke@commonspirit.org | Action Item | 2026-02-17T17:40:56.889Z
ACT-0027 | INI-0006 | Ask Tiffany About Storyboard Access for Posiitions | Marty Koepke | 2026-02-18 | Complete | 2026-02-18T19:04:53.757Z | 0ps2sv3snb0o8n93i3rgq0pjtc@google.com | Ensure all relevant positions have Social Drivers on Storyboard | marty.koepke@commonspirit.org | Action Item | 2026-02-17T18:46:17.201Z
ACT-0028 | INI-0006 | Ask Dawn Jacobson about Age Friendly Epic Gold | Marty Koepke | 2026-02-18 | Complete | 2026-02-17T21:56:43.490Z | gq2hjv40qae5c4g0mlm8grlpp0@google.com |  | marty.koepke@commonspirit.org | Action Item | 2026-02-17T18:46:59.560Z
ACT-0029 | INI-0006 | SDOH. For Cerner, evaluate workload to optimize singe form and give to Amb. | Marty Koepke | 2026-02-27 | Deferred |  | a05fjjksn66vakj5mqc5hoamhs@google.com | Review with Lisa if possible. | marty.koepke@commonspirit.org | Action Item | 2026-02-17T18:49:57.848Z
ACT-0030 | INI-0005 | Check In with Lisa Macri on Status of Data Capture | Marty Koepke | 2026-02-27 | Complete |  | 0k724ptlj1vrjbsea68u36pkvk@google.com | Per last email from Lisa, she was waiting for data to determine next steps | marty.koepke@commonspirit.org | Action Item | 2026-02-17T21:59:49.738Z
ACT-0031 | INI-0004 | Ask Heather for Risk Resource | Marty Koepke | 2026-02-20 | Complete |  | unpe9tih00rbuk27h31u9nu80g@google.com |  | marty.koepke@commonspirit.org | Action Item | 2026-02-18T23:02:00.732Z
ACT-0032 | INI-0002 | FU: What build should we expect for OB? | Marty Koepke | 2026-02-20 | Complete |  | 18ksg05a8cf0dc7d74i1okhosc@google.com |  | marty.koepke@commonspirit.org | Follow-Up | 2026-02-19T19:29:21.909Z
ACT-0033 | INI-0017 | FIle Documents by the end of the week | Me | 2026-02-20 | Deferred |  | hk3kd97i1tj07tnoo8soq2ec1o@google.com |  |  | Action Item | 2026-02-19T23:27:36.026Z
ACT-0034 | INI-0001 | Shawn to review RT access to Wound documentation on LDA | Shawn | 2026-03-06 | Complete |  | 3sbkkkl340chpap8mqj86remlg@google.com | Is this a security issue or is it a flowsheet setting issue? | marty.koepke@commonspirit.org, shawn.powell@commonspirit.org | Action Item | 2026-02-25T21:24:54.644Z
ACT-0035 | INI-0005 | Reach out to Cyndi and Mary Kane about EG prioritization. | Marty | 2026-03-17 | Not Started |  | l3u7k0nl7e1daahh5kdo5g2pdg@google.com |  | marty.koepke@commonspirit.org | Action Item | 2026-03-16T17:55:09.009Z

## Stakeholders
id | name | title | organization | email | phone | stakeholderType | createdAt
STK-0001 | Kevin Ochs | Mgr Rehab Services | CSH Rehab Services | kevin.ochs@commonspirit.org |  | Workgroup Lead | 2026-02-09T23:10:27.342Z
STK-0002 | Megan Savage | Mgr Rehab Services | CSH Rehab Services | Megan.Savage900@commonspirit.org |  | Workgroup Lead | 2026-02-09T23:11:05.000Z
STK-0003 | Michael Simpson | Director Acute Rehab Services | CSH Inpatient Rehab | michael.simpson2@commonspirit.org |  | Workgroup Lead | 2026-02-09T23:11:40.724Z
STK-0004 | Dr. Monique Diaz | CMIO | Physician Enterprise - California | monique.diaz@commonspirit.org |  | Executive Sponsor | 2026-02-09T23:12:12.764Z
STK-0005 | Dr. Umar Iqbal | CMIO | Physician Enterprises - Southwest | umar.iqbal@commonspirit.org |  | Executive Sponsor | 2026-02-09T23:12:32.569Z
STK-0006 | Dr. John Chelico | CMIO | CSH Physician Enterprise | john.chelico@commonspirit.org |  | Executive Sponsor | 2026-02-10T00:48:42.258Z
STK-0007 | Tracy Sklar | Sys SVP Quality | CSH Care Management | tracy.sklar@commonspirit.org |  | Executive Sponsor | 2026-02-10T00:49:24.624Z
STK-0008 | Holly Gibbs | Sys Director Violence Human Trafficking Response | CSH SDOH/Health Equity | holly.gibbs@commonspirit.org |  | IT Lead | 2026-02-10T00:49:49.128Z
STK-0009 | Deb Rockman | Sys VP Ambulatory Quality | CSH Ambulatory Quality | debra.rockman@commonspirit.org |  | Clinical Leader | 2026-02-10T00:50:08.046Z
STK-0010 | Chris March | Director Cardiopulmonary Services | CSH RT Council | chris.march@commonspirit.org |  | Practice Council Lead | 2026-02-10T00:50:27.432Z
STK-0011 | Marlene McKinley | Mgr, Respiratory Care | CSH RT Council | marlene.mckinley@commonspirit.org |  | Practice Council Lead | 2026-02-10T00:50:49.716Z
STK-0012 | Lisa Macri | Sys Director Clinical Tech Practice Integration | CSH Language/Interpretation | lisa.macri@commonspirit.org |  | Executive Sponsor | 2026-02-10T00:51:23.046Z
STK-0013 | Connie Clemmons-Brown | Sys SVP Patient Care Professional Practice | CSH NPPC Leader | connie.clemmonsbrown@commonspirit.org |  | Executive Sponsor | 2026-02-10T00:51:39.770Z
STK-0014 | SCI Leadership | SCI Leadership | System Informatics |  |  | Other | 2026-02-10T00:52:16.600Z
STK-0015 | Heather Miller | Sys Director Physician Engagement and Health Equity Rpting | CSH SDOH/Health Equity | heather.miller@commonspirit.org |  | Workgroup Lead | 2026-02-10T00:58:39.045Z
STK-0016 | Jessica Merritt | PES | DH - Sacramento | jessica.merritt2@commonspirit.org |  | Other | 2026-02-10T18:01:02.371Z
STK-0017 | Tammie Trefz | Sys Clinical Informatics | Quality | tammie.trefz@commonspirit.org |  | Other | 2026-02-10T18:02:10.225Z
STK-0018 | Dr. Ankita Sagar | Sys VP Clinical Transformation and Well Being | CSH Clinical Transformation | ankita.sagar@commonspirit.org |  | Executive Sponsor | 2026-02-10T18:03:00.023Z
STK-0019 | Cyndi Melden | System CI Director | CSH System Clinical Informatics | cyndi.melden@commonspirit.org |  | SCI Leader | 2026-02-10T18:03:46.621Z
STK-0020 | Jacy Rogel | IT Product Owner | CSH Engagement & Automation | jacy.rogel@commonspirit.org |  | Executive Sponsor | 2026-02-10T18:05:52.448Z
STK-0021 | Desiree Smith | IT Project Manager | IT Software Architecture | desiree.smith036@commonspirit.org |  | Other | 2026-02-10T18:06:42.891Z
STK-0022 | Patricia Harrison | IT Sr. Project Manager | DHT Shared Services | patricia.harrison@commonspirit.org |  | Other | 2026-02-10T18:07:29.168Z
STK-0023 | Erica Shimkus | Care Base Advanced Practice Provider | Virtual Care | erica.shimkus@commonspirit.org |  | Clinical Leader | 2026-02-10T18:08:08.810Z
STK-0024 | Brenda Miner | Sys Manager Virtual Nursing Continuum of Care | CSH Centralized Care | brenda.miner501@commonspirit.org |  | Clinical Leader | 2026-02-10T18:08:45.679Z
STK-0025 | Mike Dillard | Reg CI Manager | AZ CI Manager | michael.dillard@dignityhealth.org |  | Other | 2026-02-10T18:14:15.939Z
STK-0026 | Seshat McDaniel | IT Project Manager | CSH IT | seshat.mcdaniel@commonspirit.org |  | IT Lead | 2026-02-10T18:15:00.045Z
STK-0027 | Norah Loker | PES | NV Informatics | norah.loker@commonspirit.org |  | Other | 2026-02-10T18:15:42.765Z
STK-0028 | Ashley Crouse | PES | AZ Informatics | ashley.crouse@commonspirit.org |  | Other | 2026-02-10T18:16:17.425Z
STK-0029 | Demetrio Pulanco | Clinical Informaticist | MET Clinical Informatics | demetrio.pulanco@commonspirit.org |  | Other | 2026-02-11T18:37:08.021Z
STK-0030 | Jacob Scheuerman | Clinical Informaticist | SAC Clinical Informatics | jacob.scheuerman901@commonspirit.org |  | Other | 2026-02-11T18:38:00.615Z
STK-0031 | Michelle Darcy | Sys Manager Care Base Virtual Health | Virtual Care | michelle.darcy@commonspirit.org |  | Clinical Leader | 2026-02-11T18:38:54.805Z
STK-0032 | Darci Crowley | Program Mgr, Bariatric Services | Nursing Administration | darci.crowley@commonspirit.org |  | Clinical Leader | 2026-02-11T18:40:00.957Z
STK-0033 | Jay Young | IT Sr Software Engineer | EAI-ENTERPRISE APP INTEGRATION | jay.young@commonspirit.org |  | IT Lead | 2026-02-11T22:05:25.428Z
STK-0034 | Bernard Beecher | NSP Systems Analyst II | Epic HOS | bernard.beecher900@commonspirit.org |  | EHR Analyst | 2026-02-11T22:06:08.183Z
STK-0035 | Nicole Johnson | Medical Informatics Program Manager | MEDICAL INFORMATICS LEADERSHIP | nicole.johnson@commonspirit.org |  | Other | 2026-02-12T16:46:08.052Z
STK-0036 | Marty Koepke | System Clinical Informaticist | System Clinical Informatics | marty.koepke@commonspirit.org |  | Other | 2026-02-12T18:25:25.073Z
STK-0037 | Robin Roberts Drane | Sys Manager IT Applications | Learning-Strategy-Development • EPIC HOS | robin.roberts-drane@commonspirit.org |  | IT Lead | 2026-02-18T17:11:16.145Z
STK-0038 | Karen Sykes | IT EPIC Sr Application Analyst | EPIC HOS | karen.sykes@commonspirit.org |  | EHR Analyst | 2026-02-18T19:03:18.597Z
STK-0039 | Shawn Powell | IT Software Engineer | Care Pack - Epic | shawn.powell@commonspirit.org |  | EHR Analyst | 2026-02-18T19:03:53.120Z
STK-0040 | Corrinne Welch | NSP Systems Analyst II | EPIC HOS | corrinne.welch@commonspirit.org |  | EHR Analyst | 2026-02-18T20:57:31.308Z
STK-0041 | Tiffany Shields-Tettamanti | System CI Manager | CSH System Clinical Informatics | tiffany.shieldstettamanti@commonspirit.org |  | SCI Leader | 2026-02-18T22:01:48.692Z
STK-0042 | Carrie Rodriguez | SCI Manager | CSH System Clinical Informatics | carrie.rodriguez900@commonspirit.org |  | SCI Leader | 2026-02-18T22:03:19.306Z
STK-0043 | Diedre Mackey | System CI Director | CSH System Clinical Informatics | diedrey.mackey@commonspirit.org |  | Other | 2026-02-18T22:05:51.967Z
STK-0044 | Joe Robertson | Department Head | The whole deal |  |  | Executive Sponsor | 2026-02-19T23:25:37.990Z

## InitiativeStakeholders
initiativeId | stakeholderId | roleInInitiative | addedAt
INI-0003 | STK-0004 | Sponsor | 2026-02-10T00:45:47.378Z
INI-0003 | STK-0005 | Lead | 2026-02-10T00:53:29.307Z
INI-0004 | STK-0008 | Sponsor | 2026-02-10T00:55:38.055Z
INI-0005 | STK-0012 | Lead | 2026-02-10T00:56:52.395Z
INI-0005 | STK-0013 | Sponsor | 2026-02-10T00:57:07.246Z
INI-0006 | STK-0007 | Sponsor | 2026-02-10T00:58:05.403Z
INI-0006 | STK-0015 | Lead | 2026-02-10T00:59:00.521Z
INI-0001 | STK-0010 | Sponsor | 2026-02-10T01:05:04.626Z
INI-0001 | STK-0011 | Sponsor | 2026-02-10T01:05:18.974Z
INI-0008 | STK-0006 | Sponsor | 2026-02-10T01:07:49.868Z
INI-0009 | STK-0024 | Lead | 2026-02-10T18:11:23.803Z
INI-0009 | STK-0023 | Lead | 2026-02-10T18:11:42.671Z
INI-0009 | STK-0022 | Lead | 2026-02-10T18:11:56.309Z
INI-0002 | STK-0016 | Contributor | 2026-02-10T18:16:59.999Z
INI-0002 | STK-0028 | Contributor | 2026-02-10T18:17:28.913Z
INI-0002 | STK-0027 | Contributor | 2026-02-10T18:17:38.570Z
INI-0007 | STK-0026 | Lead | 2026-02-10T18:18:20.857Z
INI-0007 | STK-0025 | Lead | 2026-02-10T18:18:38.152Z
INI-0010 | STK-0009 | Sponsor | 2026-02-10T18:24:10.901Z
INI-0010 | STK-0017 | Contributor | 2026-02-10T18:24:28.891Z
INI-0010 | STK-0016 | Contributor | 2026-02-10T18:24:44.775Z
INI-0010 | STK-0019 | Lead | 2026-02-10T18:25:02.894Z
INI-0008 | STK-0020 | Lead | 2026-02-10T20:00:10.083Z
INI-0008 | STK-0021 | Lead | 2026-02-10T20:00:33.159Z
INI-0013 | STK-0023 | Sponsor | 2026-02-11T18:35:57.072Z
INI-0013 | STK-0024 | Sponsor | 2026-02-11T18:36:13.288Z
INI-0013 | STK-0029 | Contributor | 2026-02-11T18:41:14.972Z
INI-0013 | STK-0032 | Contributor | 2026-02-11T18:41:35.553Z
INI-0013 | STK-0030 | Contributor | 2026-02-11T18:42:09.822Z
INI-0003 | STK-0016 | Informatics | 2026-02-11T19:06:32.218Z
INI-0014 | STK-0006 | Sponsor | 2026-02-11T19:33:13.443Z
INI-0014 | STK-0020 | Technical Lead | 2026-02-11T19:33:37.731Z
INI-0014 | STK-0021 | Contributor | 2026-02-11T19:34:00.886Z
INI-0009 | STK-0034 | Analyst | 2026-02-11T22:08:58.226Z
INI-0009 | STK-0033 | Analyst | 2026-02-11T22:09:39.601Z
INI-0010 | STK-0035 | Informatics | 2026-02-12T16:46:42.374Z
INI-0002 | STK-0019 | Sponsor | 2026-02-12T18:16:35.255Z
INI-0002 | STK-0037 | Technical Lead | 2026-02-18T17:11:47.897Z
INI-0001 | STK-0039 | Analyst | 2026-02-18T19:04:20.657Z
INI-0001 | STK-0038 | Analyst | 2026-02-18T19:04:37.990Z
INI-0006 | STK-0040 | Analyst | 2026-02-18T20:58:13.110Z
INI-0017 | STK-0044 | Sponsor | 2026-02-19T23:27:05.746Z

## Notes
id | initiativeId | timestamp | author | noteText | noteType
NTE-0004 | INI-0006 | 2026-02-10T00:30:07.319Z | marty.koepke@commonspirit.org | Meeting scheduled with Heather Miller to review status on open items, and define next steps. Discuss Age friendly topic around exercise | Status Update
NTE-0005 | INI-0007 | 2026-02-10T18:19:29.922Z | marty.koepke@commonspirit.org | From Seshat: We are currently finalizing testing and working to complete the following by March 23rd: - Updated OBR7 segment issues - Message pool testing - Order defaulting and activation Additionally, testing, change control, and PICA must be completed. | Status Update
NTE-0006 | INI-0010 | 2026-02-10T18:26:02.758Z | marty.koepke@commonspirit.org | Review full WF in Epic Gold. Deb indicated she was working with Epic analysts, but did not provide names. Need to figure out who she has been working with. | General
NTE-0007 | INI-0003 | 2026-02-10T18:39:08.548Z | marty.koepke@commonspirit.org | message sent to Michelle Marshall and Lynn (PM) to determine feasibility of getting a new care gap added. | General
NTE-0008 | INI-0003 | 2026-02-10T20:02:22.783Z | marty.koepke@commonspirit.org | Per Karen O'Connor: We have proposed an outreach for 18 to 21 year olds but it has not been built yet as to date the markets have been focused on 3-11 and 12-17. The challenge with the 18 to 21 year olds is that they are in fact legally adults so the language would have to be tailored in that way even though CSH chose to include this subset in our definition of Well Child for the internal QA project. still need to get an ETA and communicate back to PUP | Status Update
NTE-0009 | INI-0011 | 2026-02-10T21:24:24.680Z | marty.koepke@commonspirit.org | Per Matt: This ticket had gone through full design sessions, with a final mock-up, and then after a significant period of time it was presented for voting, but unfortunately, it had been so long since the design, that new CIs had then joined, felt out of the loop, and requested that the build be put through design all over again...which was granted. From there, I have no idea what, if anything, has transpired with that ticket. | Status Update
NTE-0010 | INI-0002 | 2026-02-10T22:29:02.936Z | marty.koepke@commonspirit.org | Also reviewing SDOH build for All venues in Gold | General
NTE-0011 | INI-0002 | 2026-02-10T22:45:21.687Z | marty.koepke@commonspirit.org | Positive depression screening - fires an OPA for follow up and referrals. | Status Update
NTE-0012 | INI-0005 | 2026-02-11T17:18:06.193Z | marty.koepke@commonspirit.org | From Lisa: waiting for data so we can proceed. I understand this was backed by IT when Connie presented it recently. | Status Update
NTE-0014 | INI-0009 | 2026-02-11T17:19:58.257Z | marty.koepke@commonspirit.org | Waiting for SBAR of scope expansion to be reviewed and final decision made. | Status Update
NTE-0015 | INI-0006 | 2026-02-11T17:20:49.882Z | marty.koepke@commonspirit.org | Heather declined meeting. Rescheduled for Tuesday, 2.17.26. | Status Update
NTE-0016 | INI-0003 | 2026-02-11T17:22:23.704Z | marty.koepke@commonspirit.org | Karen O'Connor asking Gerry Alvarez and Jennifer Pennon to see if they are aware of the request. Wanting to confirm all involved parties are onboard. | Status Update
NTE-0017 | INI-0004 | 2026-02-11T18:00:49.171Z | marty.koepke@commonspirit.org | Scheduled time with Holly Gibbs to get work status update and ensure we have a good plan to keep work moving forward with Lisa's transition out. | General
NTE-0018 | INI-0006 | 2026-02-11T18:03:30.096Z | marty.koepke@commonspirit.org | EG: Review: Discuss with Tiffany at 1:1. No OPAs for + harm questions SDOH in EG No OPA for request for assistance on non harm SDOH Not in Storyboard for ED Things in Mountain, not in Gold Community Resources link > AVS Score calculation that triggers OPA for Referral to SW when | Status Update
NTE-0019 | INI-0012 | 2026-02-11T18:13:44.444Z | marty.koepke@commonspirit.org | CMU remediation SPM ticket was submitted and is in the Intake Status. | General
NTE-0020 | INI-0012 | 2026-02-11T18:14:34.247Z | marty.koepke@commonspirit.org | DMNTSK0013947 (in Intake) | General
NTE-0021 | INI-0013 | 2026-02-11T18:35:46.810Z | marty.koepke@commonspirit.org | Looking for expansion to Methodist Bariatric Services. This in unusual request as the whole team is acute only. Request is to add a new location to existing order. VV to Methodist [MET Bariatric Clinic]. Intended WF would be that acute RNs in Peri-Op would place enrollment order. VC team would send notes back to Cerner as needed and communicate to providers via TigerConnect. Work with Erica to schedule a follow up call to ensure everyone is okay with proposed solution. | Meeting Notes
NTE-0022 | INI-0008 | 2026-02-11T19:30:41.806Z | marty.koepke@commonspirit.org | Pilot phase is complete. this is now moving into expansion work. marking initiative as complete and opening a new item for longer term tracking. | Status Update
NTE-0023 | INI-0013 | 2026-02-11T20:05:35.037Z | marty.koepke@commonspirit.org | Created ticket to VV order and add Methodist Bariatric Clinic to the Clinic drop down. REQ6985711 | Status Update
NTE-0024 | INI-0013 | 2026-02-11T20:07:00.672Z | marty.koepke@commonspirit.org | RITM7164302 created | General
NTE-0025 | INI-0010 | 2026-02-11T20:17:28.831Z | marty.koepke@commonspirit.org | Turns out that Epic also has an open request, Cyndi is trying to see if we should include this in the already open Epic request. Marty to follow up on status of Epic ticket. | General
NTE-0026 | INI-0009 | 2026-02-11T22:03:56.170Z | marty.koepke@commonspirit.org | Epic analysts wanted to review the clinical WF in EG proposed build. PJ is working to set up alternate meeting time. Clinical team was not available to meet today. | Status Update
NTE-0027 | INI-0009 | 2026-02-11T22:03:58.730Z | marty.koepke@commonspirit.org | Epic analysts wanted to review the clinical WF in EG proposed build. PJ is working to set up alternate meeting time. Clinical team was not available to meet today. | Status Update
NTE-0028 | INI-0009 | 2026-02-11T22:07:27.725Z | marty.koepke@commonspirit.org | All approvals have been received by app directors. Now routing to senior leaders. SBAR meetings are on Fridays. Expecting a response in a couple of weeks. PJ following this. | Status Update
NTE-0029 | INI-0011 | 2026-02-12T00:56:08.895Z | marty.koepke@commonspirit.org | For Tiffany: Can you please review this feedback below from Matt Baugh? We need to figure out what to do with this old stale request. | Decision
NTE-0031 | INI-0010 | 2026-02-12T16:39:18.570Z | marty.koepke@commonspirit.org | Status Update Request from Cyndi following last meeting. Key Follow-Ups Evaluate the current documentation and compliance statement regarding the “other” to “plan per provider” change. Review and modify the governance documentation, adding relevant screenshots, to highlight the Cerner-specific request for leadership review. Connect with Amanda to discuss combining the Epic and Cerner optimization requests into a single governance/prioritization ticket. Evaluate the current Epic Gold build regarding documentation and follow-up plans for positive depression screenings and report the findings. Meet with Dr. Diaz to discuss the prioritization and potential impact of the Cerner change. (pending status of other items) Work on quantifying the financial risk/benefit for not making the requested change in Cerner instances to strengthen the business case. | Meeting Notes
NTE-0032 | INI-0010 | 2026-02-12T16:42:59.522Z | marty.koepke@commonspirit.org | There is an open Epic request being managed by MI Nicole Johnson. Scheduling time with her and Cyndi to review all open requests for Depression Screening Optimization to ensure continuity across platforms. | Status Update
NTE-0033 | INI-0010 | 2026-02-12T16:49:25.984Z | marty.koepke@commonspirit.org | EML Viewer that contains screenshots of Epic build for Depression Screening Interpretation. https://emlviewer-414120.uc.r.appspot.com/?state=%7B%22ids%22:%5B%2219SoikRMzgUuCj0ZW3J6okgq6WGcOPtT8%22%5D,%22action%22:%22open%22,%22userId%22:%22112645357975287998444%22,%22resourceKeys%22:%7B%7D%7D | General
NTE-0034 | INI-0007 | 2026-02-12T16:51:39.495Z | marty.koepke@commonspirit.org | Meeting Minutes Attached in Documents | Meeting Notes
NTE-0035 | INI-0010 | 2026-02-12T16:55:50.302Z | marty.koepke@commonspirit.org | From Nicole: Most everything we've talked about is in the intake slide deck that keeps growing lol. She's been adding more to it that she hasn't talked to me about (like the screenshot of Cerner). | Status Update
NTE-0036 | INI-0002 | 2026-02-12T18:05:02.280Z | marty.koepke@commonspirit.org | Checked Policy Manager and Policy STAT. Found Fall Risk policy template for markets and scribe policies. Could not find policies around 2nd BP for 140/90 or Depression Screening. Will check with quality leaders | Status Update
NTE-0037 | INI-0002 | 2026-02-12T18:16:11.314Z | marty.koepke@commonspirit.org | Sent Kelly B., Deb R. and Tammie Trefz an email about documented CSH Standards for BP, depression, TCM, MAWV. | Status Update
NTE-0038 | INI-0011 | 2026-02-12T18:35:39.632Z | marty.koepke@commonspirit.org | Sent Tiffany and email on 2.12.26 with a request for feedback. | Status Update
NTE-0039 | INI-0002 | 2026-02-12T19:15:45.448Z | marty.koepke@commonspirit.org | Link to Amb Quality Google Drive: https://drive.google.com/drive/folders/18aISkvo9X7yJUlS0-0kNyeLHs7idQa8C | Status Update
NTE-0040 | INI-0002 | 2026-02-12T19:59:13.326Z | marty.koepke@commonspirit.org | Met with Jess, Ash, Norah. Updated spreadsheet. Each given updated actions. | General
NTE-0041 | INI-0002 | 2026-02-12T22:14:29.081Z | marty.koepke@commonspirit.org | CSH Standards for Amb; https://drive.google.com/drive/folders/1eqwnKpU4mSCdDgbjr3nKAKvmTDvE6AmJ?usp=drive_link | General
NTE-0042 | INI-0010 | 2026-02-12T23:32:15.678Z | marty.koepke@commonspirit.org | Met with Nicole J. and Cyndi M. Cyndi to schedule meeting with Deb and Tammie Trefz to evaluate scope of issue and needs. Marty expressed concerns due to feedback received from Tammie about what was allowable from CMS. | Status Update
NTE-0043 | INI-0015 | 2026-02-13T00:16:05.514Z | marty.koepke@commonspirit.org | In prep of meeting tomorrow morning, reviewed both Cerner and Epic Gold and gathered screenshots of immz refusal WFs. | Status Update
NTE-0044 | INI-0001 | 2026-02-13T18:00:18.702Z | marty.koepke@commonspirit.org | Design as proposed won't work. There needs to be a way to connect device related wound documentation to specific devices for reporting. Idea 1: Add an RT device related list in wound LDA > add devices Idea 2: Add a flowsheet row > Skin integrity issue related to device > list devices Schedule time with group and include Karen Sykes. Need to evaluate Gold, and determine delta. Group informed that with current domain differences, we do not have resources to update other Epic domains. Will focus on Gold! | Meeting Notes
NTE-0045 | INI-0001 | 2026-02-13T18:05:49.335Z | marty.koepke@commonspirit.org | We also need a unique set of skin integrity check rows per flowsheet. This cannot be shared. | General
NTE-0047 | INI-0004 | 2026-02-17T17:40:03.872Z | marty.koepke@commonspirit.org | Do not forward with any effort to align current systems. For Epic Gold only to include the intervention form. Intervention form would be used regardless of referral to SW. We need space for nursing to document the intervention provided. There is an extra question of "Is mandated reporting required? Someone needs to own the decisions around mandated reporting. What needs to be in the EHR, and how to do it where info is not released and reporter is not identified. | Meeting Notes
NTE-0048 | INI-0004 | 2026-02-17T17:41:36.649Z | marty.koepke@commonspirit.org | https://docs.google.com/document/d/1PQx4J6QDFLTocvjpSB2RGpOzUgFmVocusio42dc-Ocg/edit?usp=drive_link | General
NTE-0049 | INI-0004 | 2026-02-17T17:45:55.543Z | marty.koepke@commonspirit.org | Intervention form is asking if patient was provided with extra information and resources. If SW is available, they should take this documentation, but SW is not always available so nursing needs to document what guidance the patient was given. This is being promoted because many times patients are not comfortable discussing with SW. Better rapport with nursing. | Meeting Notes
NTE-0050 | INI-0006 | 2026-02-17T18:34:29.335Z | marty.koepke@commonspirit.org | Need to know positions for Storyboard (ED, OP Surgery, Amb) ....is it RN only? other RN positions? Get a storyboard position audit. Also SDOH flowsheets. Add deficits from EG Audit. Meet with Dawn about Age Friendly. | Meeting Notes
NTE-0052 | INI-0006 | 2026-02-17T18:52:10.307Z | marty.koepke@commonspirit.org | Review Cerner for ease of updating form and giving access to all (Acute, ED, Amb). We cannot score SDOH for SW referral, we changed the questions. See if feasible to implement Community Resource link | General
NTE-0053 | INI-0006 | 2026-02-17T21:56:40.240Z | marty.koepke@commonspirit.org | scheduled time to meet with Dawn Jacobson tomorrow 2.28.26 to discuss Age Friendly. | Status Update
NTE-0054 | INI-0005 | 2026-02-17T22:00:39.743Z | marty.koepke@commonspirit.org | Set reminder invite to follow up with Lisa M on Friday, 2.27.26 | Status Update
NTE-0055 | INI-0015 | 2026-02-17T22:01:57.423Z | marty.koepke@commonspirit.org | Follow up meeting 2.18.26 with Josh and Yvette. Shared document with findings already. | Status Update
NTE-0056 | INI-0016 | 2026-02-17T22:04:32.210Z | marty.koepke@commonspirit.org | Email from Aman Bali: We were referred to you regarding planned enhancements for the Cerner Zoom integration at Dignity Health. We understand you were involved in code changes for this workflow that were tested successfully but never moved to production around 3-4 years back. Background: We are currently working to decommission Axway APIM by March and migrate all APIs to Mulesoft. The Cerner Telehealth integration is one of the final pieces remaining on Axway. While the Mulesoft development is complete, we have identified necessary changes on the consumer side (backend .NET code). In consulting with Gregg and Orlando, we discovered that several enhancements made 3-4 years ago were never deployed to production. Unfortunately, it is not possible to revert these components due to inadequate source code management tools used at that time, to focus solely on the Axway-to-Mulesoft migration. Consequently, we cannot move away from Axway without also deploying these legacy enhancements. Given the limited timeframe, we need to find a way to test these changes and workflows to ensure there is no impact on the telehealth service. Your insights on how to proceed with testing would be greatly appreciated. Let me know if a meeting is needed to align on this. Reid and Bree, I have copied you for your awareness. | General
NTE-0057 | INI-0016 | 2026-02-17T22:05:50.831Z | marty.koepke@commonspirit.org | Responded to email with request to include Cyndi Melden in an invite to review. Reid responded. "probably need to input a Zoom Change Request if you believe this will impact Zoom users or the environment". Now awaiting an invite to review. | General
NTE-0058 | INI-0016 | 2026-02-17T22:18:29.718Z | marty.koepke@commonspirit.org | Forwarded email with escalation to Cyndi and Tiff on 2.17.26 | Status Update
NTE-0059 | INI-0011 | 2026-02-17T22:19:44.097Z | marty.koepke@commonspirit.org | Sent Tiffany email escalation 2.17.26. Also added again to weekly 1:1 document. | Status Update
NTE-0060 | INI-0003 | 2026-02-17T22:30:01.017Z | marty.koepke@commonspirit.org | Sent follow up message to Karen O'Connor to determine if further conversations had occurred yet. 2.17.26 | Status Update
NTE-0061 | INI-0002 | 2026-02-17T22:33:44.934Z | marty.koepke@commonspirit.org | Attached known standards for SDOH and MA ordering Scope of Practice. Shawna is working on this with Nancy Olson WA-Tacoma. More work needs to be done on this. We don't have a system standard defined. Shawna interested in establishing a system EHR standard though. This apparently has been discussed, to formally document and apply to all MAs in the role. There is some guidance that if system has a policy and standards, then this can be accomplished. Other than that, Shawna informed me that for Nebraska and some other states they don't use MAs. They use EMTs, CNAs, and Medical Staff Assistants (MSAs), All of those scopes need to be defined as well. | Status Update
NTE-0062 | INI-0002 | 2026-02-17T22:34:55.756Z | marty.koepke@commonspirit.org | Shawna asked if I could come up with an intro concept to document System EHR standards for each role. Proposed a concept. Shawna is reviewing. | General
NTE-0063 | INI-0009 | 2026-02-18T17:03:05.562Z | marty.koepke@commonspirit.org | still waiting for final signoff by leadership review group. | Status Update
NTE-0064 | INI-0002 | 2026-02-18T17:07:08.256Z | marty.koepke@commonspirit.org | Asked for follow up on these items. @Ashley Crouse -CA testing on clinic administered meds....how is this going? @Norah Loker NV-HENDERSON Continue Depression Interp Behavior....how is this going? @Cyndi Melden AZ-PHOENIX By chance, have you been able to help narrow down the source of truth for Epic Gold WFs? Instructional Designers to reach out to? | Status Update
NTE-0065 | INI-0006 | 2026-02-18T17:09:25.671Z | marty.koepke@commonspirit.org | Sent Google Chat to Carrie and Tiffany: HI There! For SDOH, I need an audit of which position's storyboards have Social Drivers. Who would be able to get me this information? Also, who is the best resource for me to reach out to for EG SDOH build needs and questions? | Status Update
NTE-0066 | INI-0006 | 2026-02-18T17:41:04.702Z | marty.koepke@commonspirit.org | Per Dawn: There are now CMS requirements around Age Friendly. Focus now is "are we meeting it" attestation. Both EHRs did have standard content and we did not take it. That was under Karen Darling. Part of current work is evaluating if we can or what can/should we take to get caught up. 5 domains: Pt. Goals/ACP, Pt Meds, Frailty Screening (malnutrition, depression, mobility, etc.)....pulls into a navigator for quality, Social Screening (access, abuse, caregiver stress, needs) social isolation is not consistent and not in Gold, financial abuse). potential request is to expand screening questions for patients > 65. last domain is leadership (this is where CMS wants to know if someone in the Org is responsible, monitoring imp. and utilization of program). | General
NTE-0067 | INI-0006 | 2026-02-18T18:07:19.744Z | marty.koepke@commonspirit.org | Age Friendly: EG-can we constrain extra questions by age of patient, by encounter type? | Meeting Notes
NTE-0068 | INI-0001 | 2026-02-18T19:00:57.983Z | marty.koepke@commonspirit.org | CI Concerns: Content documented in Flowsheet template cross over to ALL flowsheet templates that have that same Response: Not an issue in Gold, the only flowsheet this documentation will sit in is O2/Bipap CI Concerns: We need device specific documentation in flowsheets. Response: we should not need device specific documentaiton in flowsheets. check reporting. evaluate if we can filter by role/specialty. Probably not available immediately. Would need to make a request for reporting. Karen will demo Gold next Wed to CIs. Shawn reporting to Donnie that this will be constrained to Gold build due to variability in all the other domains. | Meeting Notes
NTE-0069 | INI-0002 | 2026-02-18T19:21:11.470Z | marty.koepke@commonspirit.org | Per Tiffany: SDOH Epic Audit - Start with Epic Gold IT Analysts. If don't have an analysts contact start with Kristy Doornbos | General
NTE-0070 | INI-0006 | 2026-02-18T19:25:19.985Z | marty.koepke@commonspirit.org | Per Tiffany: SDOH Epic Audit - Start with Epic Gold IT Analysts. If don't have an analysts contact start with Kristy Doornbos | General
NTE-0071 | INI-0001 | 2026-02-18T19:36:13.421Z | marty.koepke@commonspirit.org | Karen has build complete in EG | Status Update
NTE-0072 | INI-0006 | 2026-02-18T20:56:26.843Z | marty.koepke@commonspirit.org | Per Kristy: Please work with Corrinne on your questions, and please keep in mind we need to keep in alignment with the gold build decisions....sent this name to Dawn as well. | General
NTE-0073 | INI-0011 | 2026-02-18T23:02:26.501Z | marty.koepke@commonspirit.org | Per Tiffany, close this request | Status Update
NTE-0074 | INI-0002 | 2026-02-19T19:25:51.274Z | marty.koepke@commonspirit.org | Good progress on testing. Norah has some observations regarding depression screening. Also need definition around expected MyChart for depression screening with high responses. | General
NTE-0075 | INI-0009 | 2026-02-19T21:02:50.531Z | marty.koepke@commonspirit.org | Scanning Governance had approved document type Escalated Remote Patient Monitoring. It should be in TST now (Per Grace Balajadia) | Status Update
NTE-0076 | INI-0003 | 2026-02-19T21:06:33.299Z | marty.koepke@commonspirit.org | PUP scheduled for next Thursday. Karen O'Connor attending to discuss verbiage for this new care gap outreach. Also inviting Jennifer Pennon since she has been Dr. Diaz's rep. Also engaging Ranae Forbes (Foundation Quality) and Tammie Trefz (System eCQM) for their guidance on quality reporting for Wellness Visits Ages 18-21 years. | General
NTE-0077 | INI-0015 | 2026-02-19T21:50:52.212Z | marty.koepke@commonspirit.org | Goal from Josh is to document that our EHRs have the ability to document Immz/Vaccine refusals/deferrals. Epic, Cerner definitely have the ability to document Immz refusal both outside the order entry WF as well as documenting once ordered as a reason for not giving. Screenshots from Epic and Cerner provided. | General
NTE-0078 | INI-0015 | 2026-02-19T22:58:00.275Z | marty.koepke@commonspirit.org | Updated document with more screenshots from Epic. Josh to review and determine if this is sufficient to bring to PAG. | General
NTE-0079 | INI-0017 | 2026-02-19T23:24:41.955Z | marty.koepke@commonspirit.org | Here are some notes that I want to have in here | General
NTE-0080 | INI-0017 | 2026-02-19T23:26:42.565Z | marty.koepke@commonspirit.org | Some really important things just happened that need to be noted. | General
NTE-0081 | INI-0005 | 2026-02-20T19:58:13.351Z | marty.koepke@commonspirit.org | Email from Lisa: I am writing to ensure we are coordinating our efforts regarding the EHR language updates. I have been working with the NW region to address a Department of Justice lawsuit, which requires specific EHR changes to ensure compliance. During our last meeting, we discussed consolidating our efforts to ensure these updates are implemented consistently across the board, and in a timely manner. My Supply Chain partner is currently reviewing vendor data to produce actionable materials for the project. In the meantime, I want to ensure we are aligned and prepared to move forward together. Please let me know if there are any additional steps I should complete at this stage. | General
NTE-0082 | INI-0004 | 2026-02-24T22:30:54.296Z | marty.koepke@commonspirit.org | Met with Chasity, Holly and Shanda. They agree that next steps is to meet with Beth Miller to discuss IRIS and if this is a more appropriate place to document staff reporting of mandated reporting, instead of EHR so staff names are not released with this information accidentally with EHR records, even if quarantined off. | Status Update
NTE-0083 | INI-0001 | 2026-02-25T19:55:58.262Z | marty.koepke@commonspirit.org | Group felt good about the design for Epic Gold. Brian FAwn wants to check out Cogito to determine reportability on device related skin issues. | General
NTE-0084 | INI-0001 | 2026-02-25T19:55:59.248Z | marty.koepke@commonspirit.org | Group felt good about the design for Epic Gold. Brian FAwn wants to check out Cogito to determine reportability on device related skin issues. | General
NTE-0085 | INI-0001 | 2026-02-25T19:56:02.812Z | marty.koepke@commonspirit.org | Group felt good about the design for Epic Gold. Brian FAwn wants to check out Cogito to determine reportability on device related skin issues. | General
NTE-0086 | INI-0001 | 2026-02-25T20:42:09.074Z | marty.koepke@commonspirit.org | scheduled meeting with Jonathan Pesta for next Tuesday 3.3.26 | Status Update
NTE-0087 | INI-0017 | 2026-03-12T18:50:53.294Z | marty.koepke@commonspirit.org | I need to add a new note for review | General
NTE-0088 | INI-0005 | 2026-03-16T17:54:19.936Z | marty.koepke@commonspirit.org | Met with Meagan Mangus, Lisa M. and Melissa Plummer. Discussed clarification for interpreter engagement documentation for patient and staff. also reviewed intro concept for metrics/reporting needed for both internal compliance and state reporting. Reaching out to Cyndi and Mary Kane to ensure this can be added as high priority on EG System policy list. | Meeting Notes

## Documents
id | initiativeId | documentName | documentType | driveUrl | dateAdded
DOC-0003 | INI-0002 | W3 TST User Logins | Other | https://docs.google.com/spreadsheets/d/1OhbMI0VP6NgOAgc_wAaO9nMUOKVU6ZbkcMyMaWDRR8g/edit?gid=1917524021#gid=1917524021 | 2026-02-09T23:18:07.097Z
DOC-0004 | INI-0002 | Epic Gold TST Login | Other | https://docs.google.com/document/d/1yssaqZ4Ezq3wXVqroksvlFmx1RKmpAf0eP9XwCviHcM/edit?tab=t.0 | 2026-02-09T23:18:41.458Z
DOC-0005 | INI-0002 | W3 Master Location List | Other | https://docs.google.com/spreadsheets/d/1CyJTUedftq1hNHRF8D6InOqahGmzLQPl4Bwf7TXhVR4/edit?gid=0#gid=0 | 2026-02-09T23:18:45.458Z
DOC-0006 | INI-0002 | Epic Gold Amb WFs |  | https://docs.google.com/spreadsheets/d/1lQqOmB_wUOP5BU90Zf7AUJmD3CBBGQcW9YEyAalpakg/edit?gid=1473215283#gid=1473215283
DOC-0011 | INI-0006 | SDOH Clinical Define Slides | Requirements | https://docs.google.com/presentation/d/1_JlJ5zEueI2YDZOuxt2yNFqyCgO4_w5zKN4MITRfbfc/edit?slide=id.geaa92738cc_0_0#slide=id.geaa92738cc_0_0 | 2026-02-10T00:30:50.161Z
DOC-0012 | INI-0006 | SDOH SCI EHR Requirements Document | Requirements | https://docs.google.com/spreadsheets/d/1MXA_AM_1vyN796h6GDU29ZyLvPlBq1PFF9LyQlGS0u8/edit?gid=1066389553#gid=1066389553 | 2026-02-10T00:31:28.987Z
DOC-0013 | INI-0006 | SDOH CSH Approved Questions Crosswalk | Requirements | https://docs.google.com/spreadsheets/d/1x-oV2DVQ69TBk9TQYZ5g8kRFPG3VfHRu2vCF_t73jqM/edit?gid=1444884198#gid=1444884198 | 2026-02-10T00:32:01.551Z
DOC-0014 | INI-0006 | Meeting Agenda-Heather/Marty Check In 2.12.26 | Business Case | https://docs.google.com/document/d/1NLW64iNDCQssY-0IKGu7vx99jFzuRLDP16wl0Y3Ab6k/edit?tab=t.0 | 2026-02-10T00:32:58.367Z
DOC-0015 | INI-0005 | Translation Working Folder (Non Ticket) | Business Case | https://drive.google.com/drive/folders/11poDwVlKnclZtuDdkQgPRLxxs8TMyZ4d | 2026-02-10T00:37:28.687Z
DOC-0016 | INI-0005 | Epic Gold Design Proposal | Business Case | https://docs.google.com/spreadsheets/d/1fbwBgPteaPWnmdkzz1-2J4JA0878oRDj3cv_7-5XKrE/edit?gid=0#gid=0 | 2026-02-10T00:38:14.217Z
DOC-0017 | INI-0006 | CMS Standard Screening Tool | Requirements | https://www.cms.gov/priorities/innovation/files/worksheets/ahcm-screeningtool.pdf | 2026-02-10T01:11:36.802Z
DOC-0018 | INI-0002 | Norah EG Amb Testing | Other | https://docs.google.com/document/d/19hOO9rOmzFjQs6ZVSfKglJFpMM6BXQ00r86oSnNKCkI/edit?tab=t.0 | 2026-02-11T17:38:18.365Z
DOC-0019 | INI-0010 | Epic Depression Optimization Business Case | Business Case | https://docs.google.com/presentation/d/1f5G5Xv07Jxbf_z2gx8XINye-8YvqKpwBXo1tRiWUOLo/edit?slide=id.g2ccdbaf18e2_0_322#slide=id.g2ccdbaf18e2_0_322 | 2026-02-12T16:43:42.339Z
DOC-0020 | INI-0010 | EML Email of Epic Gold Build for Depression Interpretation FU. | Other | https://emlviewer-414120.uc.r.appspot.com/?state=%7B%22ids%22:%5B%2219SoikRMzgUuCj0ZW3J6okgq6WGcOPtT8%22%5D,%22action%22:%22open%22,%22userId%22:%22112645357975287998444%22,%22resourceKeys%22:%7B%7D%7D | 2026-02-12T16:50:12.209Z
DOC-0021 | INI-0007 | Natera Minutes 2.12.26 | Business Case | chrome-extension://efaidnbmnnnibpcajpcglclefindmkaj/https://mail.google.com/mail/u/0?ui=2&ik=cfe1f6e5c7&attid=0.1&permmsgid=msg-f:1856938971912477826&th=19c52c280e6c1c82&view=att&disp=inline&realattid=f_mljp0ln60&zw&acrobatPromotionSource=gmail_chrome-card | 2026-02-12T16:52:03.811Z
DOC-0026 | INI-0015 | Cerner Immz Refusal Screenshots | Other | https://docs.google.com/document/d/19Dbj6Op3dj53shTR680ZY1BHpKp5XEgmHVBDnPIsXEg/edit?tab=t.0 | 2026-02-12T18:49:03.504Z
DOC-0030 | INI-0002 | CSH Amb Clinical Standards Drive Folder | Policy | https://drive.google.com/drive/folders/1eqwnKpU4mSCdDgbjr3nKAKvmTDvE6AmJ?usp=drive_link | 2026-02-12T22:15:55.210Z
DOC-0031 | INI-0002 | Epic Gold ClinDoc Team Names | Business Case | https://docs.google.com/spreadsheets/d/1G7cvovhpxX3ILVExlMsb8gMI5AVva3Ha97-pcGU7OC8/edit?gid=0#gid=0 | 2026-02-12T22:16:46.836Z
DOC-0032 | INI-0001 | RT HAPI Skin Design Approved | Design Spec | https://docs.google.com/spreadsheets/d/1ViIedhzeNyOrOKTpMj_TXzQNT97N2WoDktMmPhgLcH4/edit?gid=0#gid=0 | 2026-02-13T16:04:20.553Z
DOC-0033 | INI-0001 | 2.23.26 Meeting Minutes | Meeting Notes | https://emlviewer-414120.uc.r.appspot.com/?state=%7B%22ids%22:%5B%22122YRKqCPm4hDo60O3UffFtkp-Rncbtra%22%5D,%22action%22:%22open%22,%22userId%22:%22112645357975287998444%22,%22resourceKeys%22:%7B%7D%7D | 2026-02-13T18:23:09.569Z
DOC-0034 | INI-0004 | Lisa's Duplication Screenshot Workbook | Other | https://docs.google.com/spreadsheets/d/16aPBgiYBEKp52WMN-8D7HnwvLCZwZy3n5pnUgdfjA4A/edit?gid=0#gid=0 | 2026-02-17T17:28:50.571Z
DOC-0035 | INI-0004 | Abuse Neglect Cerner Audit - Lisa | Business Case | https://docs.google.com/spreadsheets/d/1mjrak34aZlXcyKjJYydH-JShsdhEYyJBm8W5G0l5UHc/edit?gid=1646881245#gid=1646881245 | 2026-02-17T17:29:35.334Z
DOC-0036 | INI-0004 | Background On Screening and Intervention Forms | Other | https://docs.google.com/document/d/1PQx4J6QDFLTocvjpSB2RGpOzUgFmVocusio42dc-Ocg/edit?usp=drive_link | 2026-02-17T17:42:06.597Z
DOC-0037 | INI-0004 | Topic Refresh Summary 2.17.26 (Holly/Marty) | Meeting Notes | https://emlviewer-414120.uc.r.appspot.com/?state=%7B%22ids%22:%5B%221z_GtEnFLT-b1kIQykXRdHjLrXB10yzi4%22%5D,%22action%22:%22open%22,%22userId%22:%22112645357975287998444%22,%22resourceKeys%22:%7B%7D%7D | 2026-02-17T17:55:45.559Z
DOC-0038 | INI-0006 | Gold Readiness Audit Workbook (SCI Team) | Other | https://docs.google.com/spreadsheets/d/1rq45ZkY7pWVoRcEFE0vR8oMQjAMAdJp-CIVyNCIIvNk/edit?gid=1363818461#gid=1363818461 | 2026-02-17T19:13:29.091Z
DOC-0039 | INI-0016 | Original Project Follow Ups | Requirements | https://docs.google.com/document/d/1vBBIoNrTh9mARlMr9ZIV61PFxy4zyAU1xILaPmY-ydM/edit?tab=t.0 | 2026-02-17T22:07:21.765Z
DOC-0040 | INI-0002 | Concept EHR Standard Configuration by role (MA, CNA, EMT, MSA = Amb) | Other | https://drive.google.com/drive/folders/1TcmFIMyYgKtLhoFGoKbu2xK0f6fGXitQ | 2026-02-17T22:35:42.497Z
DOC-0041 | INI-0009 | HRS SBAR for extra scope | Business Case | https://docs.google.com/document/d/1xEgzdrXAhw7QUWGJstq1qNZ16WPF65Lr/edit | 2026-02-18T17:01:54.571Z
DOC-0042 | INI-0015 | Immz CSH Guidelines | Policy | https://docs.google.com/document/d/1v2VEcoopnafQPcwemNNeQmWylwF4Jd3slzjqNhzURyA/edit?tab=t.0 | 2026-02-19T21:59:25.889Z
DOC-0043 | INI-0017 | Initiative Business Case | Business Case | https://docs.google.com/spreadsheets/d/1qeygJUNANZ8-OTSR8wY1-zsZ5Wj8IKCDSyYa8QRwDVI/edit?gid=0#gid=0 | 2026-02-19T23:28:23.431Z
DOC-0044 | INI-0001 | Mountain Maintenance Request | Design Spec | https://docs.google.com/document/d/1vYhfdBxnIJtYg4Jqw90-XMnFd1kRxwIxVPm4xKB2yGU/edit?tab=t.0 | 2026-03-16T19:50:04.170Z

## Governance
id | initiativeId | ticketNumber | submissionDate | reviewDate | status | conditions | decisionDate | updatedAt
GOV-0001 | INI-0002 |  |  |  | Drafting |  |  | 2026-03-13T20:59:52.822Z

## Metrics
id | initiativeId | metricName | unit | preValue | preDate | preTimeframe | targetValue | postValue | postDate | postTimeframe | notes | createdAt
MET-0001 | INI-0001 | Dev Time | Hours | 420 | 2025-11-04 |  | 50 | 16 | 2026-02-06 |  |  | 2026-02-10T19:45:55.708Z
MET-0002 | INI-0001 | Dev Cost | $ | 27500 | 2026-01-06 |  | 5000 | 890 | 2026-02-04 |  |  | 2026-02-10T19:46:51.277Z
MET-0003 | INI-0008 | Documentation Time per Note | Minutes | 68.66 | 2025-04-01 |  |  | 58.04 | 2026-01-01 |  |  | 2026-02-10T19:58:55.076Z
MET-0004 | INI-0008 | Increased RVUs | $ | 276699 | 2025-04-01 |  |  | 29557 | 2026-01-01 |  |  | 2026-02-10T19:59:49.015Z
MET-0005 | INI-0017 | Reduce Cognitive Load | % | 95 | 2026-01-01 | Nov-Dec 25 | 30 |  |  |  |  | 2026-02-19T23:29:22.997Z

## Config
key | value
nextActionItemId | 36
nextNoteId | 89
nextInitiativeId | 18
nextStakeholderId | 45
nextDocumentId | 45
weeklyReportEnabled | TRUE
weeklyReportDay | MONDAY
weeklyReportHour | 8
weeklyReportRecipients | marty.koepke@commonspirit.org
calendarSendInvites | TRUE
calendarEventDuration | 30
calendarEventHour | 9
nextMetricId | 6
eodScheduleEnabled | FALSE
eodScheduleHour | 17
eodScheduleRecipients | marty.koepke@commonspirit.org
nextGovernanceId | 2